## IDIQ LOG FACILITIES
WO Number | Description | Asset Number | Bldg. | Zone | Site | IDIQ Type | LOL | Status of Job | Party Performing Work | Work Order Received | Date of Site Visit | POP (days) | Proposal Amount | Submitted to Government | Days with Jacobs | Days with Gov't | Government Award Date | Pre-Con Date | Estimated Completion Date (ECD) | Actual Completion Date | QA Sign-Off | PAR Sign-Off Date | Invoice Date | Notes | Jacobs POC | Event
FINISHED/Complete
EXECUTION
SUBMITTED
| FUNDED BY OTHERS | [11 empty] | 0
IN-KIND
WAITING FUNDING
ON THE SHELF
BREAK-DOWN LIST
Cancelled

## IDIQ LOG UTILITIES
IDIQ Progress Log | [5 empty] | Suggested search technique: use filters to find work order # or bldg. #. Data may be hidden if filters are in place.
As of: | 2024-12-04 |  |  |  |  | To clear filters, click "Data" tab on the top menu, "sort & filter" on the ribbon, then click "clear"
Priority | Critical Date | Next Action | WO Number | Description | Asset Number | Bldg. | Site | Utility | IDIQ Type | LOL | Status of Job | Party Performing Work | Work Order Received | Date of Site Visit | POP (days) | Proposal Amount | Submitted to Government | Days with Jacobs | Days with Gov't | Government Award Date | Pre-Con Date | Estimated Completion Date (ECD) | Actual Completion Date | QA Sign-Off | PAR Sign-Off | Invoice Date | Notes | Jacobs POC | Event
|  |  |  | FINISHED/Complete | [11 empty] | #REF!
EXECUTION
SUBMITTED
FUNDED BY OTHERS
IN-KIND
WAITING FUNDING
ON THE SHELF
BREAK-DOWN LIST
Cancelled

## REPORT (hidden)
| current as of | 2024-12-04
FACILITIES
| Row Labels | Count of Status of job | [8 empty] | Facilites |  | Utilites |  | BSVE
| Complete | 10 | [8 empty] | Submitted |  | Submitted |  | Submitted
| Invoice Rejected | 2 | [8 empty] | Start | 2023-08-01 | Start | 2023-08-01 | Start | 2023-08-01
| Invoiced | 163 | [8 empty] | End | 2023-08-31 | End | 2023-08-31 | End | 2023-08-31
| Ready for Invoice | 1 | [8 empty] | Count | 0 | Count | 0 | Count | #REF!
| Pending Invoice Approval | 13
| Grand Total | 189
Facilites
Funded
[11 empty] | Start | 2023-08-01
[11 empty] | End | 2023-08-31
Count
[11 empty] | Amount | 206373.97 | 138783.95 | 1650.48 | 346808.4
UTILITIES
| Row Labels | Count of Status of job
| Complete | 10
| Invoiced | 95 | [8 empty] | Sub-Total Function
| Pending Invoice Approval | 8 | [8 empty] | Current Month Awards (filter on tabs needed) |  |  | < | 100000
| Ready for Invoice | 1 | [11 empty] | 101000 | 200000
| Grand Total | 114 | [8 empty] | 0 | FAC |  | 201000 | 499999
[11 empty] | #REF! | Utility |  | 500000 | 749999
| BSVE | [9 empty] | #REF! | BSVE |  | > | 750000
| Row Labels | Count of Status of Job | [8 empty] | #REF!
| Complete | 17
| Invoiced | 13
| Pending Invoice Approval | 2
| Grand Total | 32
| 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | Total |  | Average
| 3547019.46 | 99514.06 | 456845.21 | 636385.41 | 352474.77 | 74525.59 | 2500 | 443726.71 | 1192586.07 | 23441.03 | 96249.67 | 99689 | 7024956.98 |  | 585413.0817
| 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
| 22353.71 | 120360.16 | 91058.98 | 408385.42 | 116224.24 | 329898.97 | 75557.16 | 438344.98 | 370831.12 | 261249.95 | 132894.9 | 112255.58 | 2479415.17 |  | 206617.9308
| 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
| 95988.79 | 213503.98 | 1125889.01 | 254936.55 | 361807.96 | 208327.22 | 309473.12 | 141955.17 | 745110.96 | 235839.97 | 61809.91 | 360457.07 | 4115099.71 |  | 342924.9758
| 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
| 506195.78 | 289194.7 | 1666245.82 | 30929.71 | 23230.63 | 89283.41 | 58919.02 | 260016.28 | 489356.65 | 362299 | 161420.87 | 1162416.45 | 5099508.32 |  | 424959.0267
4720
[8 empty] | 2023-08-23 |  | 357579
| 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 |  |  |  | Annualized
| 161013.82 | 46021.51 | 299788.35 | 211561 | 635832.95 | 1450827.14 | 776087.58 | 346808.46 | 0 | 0 | 0 | 0 | 3927940.81 |  | 523725.4413 | 6284705.296
[5 empty] | 1354217.63 | 2573723.18
Month Total | 4332571.56 | 768594.41 | 3639827.37 | 1542198.09 | 1489570.55 | 2152862.33 | 1222536.88 | 1630851.6 | 2797884.8 | 882829.95 | 452375.35 | 1734818.1 | 22646920.99
Average | 866514.312 | 153718.882 | 727965.474 | 308439.618 | 297914.11 | 430572.466 | 244507.376 | 326170.32 | 699471.2 | 220707.4875 | 113093.8375 | 433704.525
|  | Total | Average Per Month | Annualized |  | Fees and Profit (9.5%) | Monthly Avg Fee and Profit (9.5%) | Profit 6.5%
13 Months | July 22- Current | 5259952.63 | 375710.9021 | 5259952.63 | Joe & John | 499695.4999 | 35692.5357 | 341896.9209 |  | 2023 | 3209556.13
42 Months | Jan 19 to July 22 | 16224551.91 | 386298.855 | 4635586.26 | Everyone else | 1541332.4315 | 36698.3912 | 1054595.8742 |  | 2022 | 171433.06 | -3038123.07
[10 empty] | 2021 | 879608.3 | -2329947.83
[10 empty] | 2020 | 521680.37 | -2687875.76
[10 empty] | 2019 | 429500.36 | -2780055.77
Note on K54: Armstrong, John: IAN Funded
Note on K55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IAN

## Breakdown (hidden)
WO Number | Description | Asset Number | Bldg. | Zone | Site | IDIQ type | LOL | Status of Job | Party Performing Work | Work Order Received | Date of Site Visit | POP (days) | Proposal Amount | Submitted to Government | Days with Jacobs | Days with Gov't | Government Award Date | Pre-Con Date | Estimated Completion Date (ECD) | Actual Completion Date | QA Sign-Off | PAR Sign-Off Date | Invoice Date | Notes | Jacobs POC
| Compressor Air | MYP-2025-VAC-01 | MAYPOR-2025 |  |  | BREAKDOWN |  | BREAKDOWN | Tagged out of service, inoperable | [14 empty] | Tagged out of service, inoperable | Dave Strickland
| Compressor Air - Heckscher Fuel Farm | A134426 | MAYFISC-104 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable, controller needs to be replaced. IDIQ work order 853187 waiting approval | [14 empty] | Inoperable, controller needs to be replaced. IDIQ work order 853187 waiting approval WO 1339745 servicing temp compressor until original is fixed | Dave Strickland
| Air Compressor #1 | A131094 | MAYPOR-1586 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Air Compressor #2 | A131095 | MAYPOR-1586 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Air Compressor #1 | A131081 | MAYPOR-1585 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Air Compressor #2 | A131082 | MAYPOR-1585 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Air Compressor (For Control Air) | A131118 | MAYPOR-1587 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Air Compressor (For Control Air) | A131119 | MAYPOR-1587 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, electronic controls installed | [14 empty] | Abandoned, electronic controls installed | Dave Strickland
| Compressor - Drier Air - Chapel | A116040 | MAYPOR-350 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| PM - Roll Gate 191 East - DLA | MYP-191-RG-02 | MAYPOR-191 |  |  | BREAKDOWN |  | BREAKDOWN | Electric gate - inoperable due to bad control board. IDIQ WO 919593 sent for approval- Ricky Shepheard cancelled request on 4/30/21. | [14 empty] | Electric gate - inoperable due to bad control board. IDIQ WO 919593 sent for approval- Ricky Shepheard cancelled request on 4/30/21. | Dave Strickland
| Door Powered R/U #1 of 6 | MYP-1430-EOD-01 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Door Powered R/U #2 of 6 | MYP-1430-EOD-02 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Door Powered R/U #3 of 6 | MYP-1430-EOD-03 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Door Powered R/U #4 of 6 | MYP-1430-EOD-04 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Door Powered R/U #5 of 6 | MYP-1430-EOD-05 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Door Powered R/U #6 of 6 | MYP-1430-EOD-06 | MAYPOR-1430 |  |  | BREAKDOWN |  | BREAKDOWN | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | [14 empty] | Corroded, no longer functional, IDIQ work order 1492882 waiting approval | Dave Strickland
| Fans Exhaust - Fan Roof, Direct Drive - Hsl46 roof | A116272 | MAYPOR-1552 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable, shafts seized. IN-KIND WO 731356 waiting approval | [14 empty] | Inoperable, shafts seized. IN-KIND WO 731356 waiting approval WO 1075789 Exhaust fan in good working order some rust did some corrosion control. | Dave Strickland
| Boiler Sys - Bldg. 1960 - Water Heat - Hot Water | A117280 | RIBBAY-1960 |  |  | BREAKDOWN |  | BREAKDOWN | Out of service | [14 empty] | Out of service - emailed Tim | Dave Strickland
| Boiler Sys - Bldg. 2105 - Heat/HVAC | A117291 | MAYPOR-2105 |  |  | BREAKDOWN |  | BREAKDOWN | Out of service, IDIQ work order 984495 in progress | [14 empty] | Out of service, IDIQ work order 984495 in progress - emailed Tim | Dave Strickland
| Boiler Sys - Bldg. 1552 - Hot Water | MYP-1552-WCG-04 | MAYPOR-1552 |  |  | BREAKDOWN |  | BREAKDOWN | Out of service, IDIQ work order 1293338 waiting approval | [14 empty] | Out of service, IDIQ work order 1293338 waiting approval - emailed Tim | Dave Strickland
| Boiler Sys - Bldg. 191 - Firetube - Heat/HVAC - York Shipley | A117239 | MAYPOR-191 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used | Dave Strickland
| Air Cooled Chiller | A130676 | MAYPOR-351 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable, IDIQ work order 1194865 Approved, WMATL. | [14 empty] | Inoperable, IDIQ work order 1194865 Approved, WMATL. wo 1346996 pm completed | Dave Strickland
| Condenser Unit Located out on the point | A131973 | MAYPOR-2211 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable, bldg. unoccupied | [14 empty] | Inoperable, bldg. unoccupied may need to send ROM | Dave Strickland
| Air Handler | A131974 | MAYPOR-2211 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable, bldg. unoccupied | [14 empty] | Inoperable, bldg. unoccupied may need to send ROM | Dave Strickland
| DX Straight Cool Air Handling Unit with heat (note: condenser still operable) | A134698 | MAYPOR-1391 |  |  | BREAKDOWN |  | BREAKDOWN | Inoperable | [14 empty] | Inoperable may need to send ROM | Dave Strickland
| Ductless Split System - Air Handler 2 Ton - Computer Cove | A132423 | MAYPOR-245 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used. | [14 empty] | Abandoned, no longer used. | Dave Strickland
| Ductless Split System - Condensing Unit 2 Ton - Mezzanine | A132424 | MAYPOR-245 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used. | [14 empty] | Abandoned, no longer used. | Dave Strickland
| Low Sulfur Diesel Fuel - 350 Gal - FISC(s side FP) 191B (Zone 1) | A117906 | MAYPOR-191 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used | Dave Strickland
| Aboveground Tank - Bldg. 1553 - Used Oil, 1553-2, 300 Gallon (ZONE 3) | A117505 | MAYPOR-1553 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used may need to send ROM - wo 1697602 states oil level empty - do we still need to pm? | Dave Strickland
| Above ground Tank - Bldg. 1553 - Used Oil - N1553 500GL (ZONE 3) | A117506 | MAYPOR-1553 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used may need to send ROM - wo 1530224 states leak gauge empty - do we still need to pm? | Dave Strickland
| Aboveground Tank - Bldg. 1587 - Fuel Oil, Heating, 2287 Day Tank, Fuel in Secondary Containment (Zone 1) | A117490 | MAYPOR-1587 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used may need to send ROM - wo 1697534 states fuel level empty - do we still need to pm? | Dave Strickland
| Aboveground Tank - Bldg. 471 - Diesel, Emer Gen - G471 1000 gal (Zone 4) | A117433 | MAYPOR-471 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Aboveground Tank - Bldg. 1 - Fuel Oil, 50 Gallons (Zone 1) | A137915 | MAYPOR-1 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Underground Tank - Bldg. 1363 - Fuel Oil, Heating, N1363, 7,500 Gal (Zone 1) | A117479 | MAYPOR-1 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Underground Tank - Bldg. 1488 - Used Oil - N1490 Used oil 2K (ZONE 2) | A117501 | MAYPOR-1488 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Above Ground Tank, 2000 Gallon - Used Oil (Zone 4) | MYP-1488-AGT-03 | MAYPOR-1488 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Above Ground Tank, 10000 Gallon - Fuel Oil (Zone 4) | MYP-1488-AGT-04 | MAYPOR-1488 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Underground Tank - Bldg. 1338 - Used Oil - N1342, 560 Gallons (Zone 3) | A117497 | MAYPOR-1342 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Underground Tank - Bldg. 1461 - Used Oil/Separator C1 Pier | A117499 | MAYPOR-1461 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Aboveground Tank - Bldg. 1552 - Diesel - N1552, 250 Gallons (ZONE 3) | A117514 | MAYPOR-1552 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used may need to send ROM - wo 1697656 states fuel level empty - do we still need to pm? | Dave Strickland
| Aboveground Tank 2208 - Bldg. 1878 (Zone 2) - Diesel, Emer Gen, 600 GAL | A117451 | MAYPOR-1878 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed and replaced with natural gas line | [14 empty] | Does not exist, removed and replaced with natural gas line | Dave Strickland
| Aboveground Tank - Bldg. 191 - Fuel Oil, Heating- Tank N191A, 6000 Gallons (Zone 1) | A117456 | MAYPOR-191 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used but contains fuel oil | [14 empty] | Abandoned, no longer used but contains fuel oil may need to send ROM but tank contains fuel so keep pm on | Dave Strickland
| Aboveground Tank - Bldg. 2105 - Fuel Oil, 3500 Gallons | MYP-2105-AGT-01 | MAYPOR-2105 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Does not exist, removed | Dave Strickland
| Aboveground Tank - Bldg. 349 - Fuel Oil, Heating - Tank 2268, 350 Gallons (Zone 1) | A117464 | MAYPOR-349 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used (supports deteriorated) | [14 empty] | Abandoned, no longer used (supports deteriorated) may need to send ROM - wo 1697506 states fuel level empty - do we still need to pm? | Dave Strickland
| Grease and Grit Traps - Car Wash | A117790 | MAYPOR-1316 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no longer used | [14 empty] | Abandoned, no longer used | Dave Strickland
| Chiller | A130690 | MAYPOR-351 |  |  | BREAKDOWN |  | BREAKDOWN | Temporary chiller in place, asset is inoperable | [14 empty] | Temporary chiller in place, asset is inoperable | Dave Strickland
| Tankless Hot Water Heater - Use: Heat/Vac (1 OF 1) | A134758 | MAYPOR-413 |  |  | BREAKDOWN |  | BREAKDOWN | Bldg. under renovations, Noritz unit removed. Switching to gas fired system. | [14 empty] | Bldg. under renovations, Noritz unit removed. Switching to gas fired system. | Dave Strickland
| Backflow Devices 2" - RP - Southside of bldg. | MYP-3-BFP-00 | MAYPOR-3 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Should be removed from 1502000-22 in future mod | Dave Strickland
| Backflow Devices - RP 1.5"- Westside of bldg. | MYP-1600-BFP-04 | MAYPOR-1600 |  |  | BREAKDOWN |  | BREAKDOWN | Does not exist, removed | [14 empty] | Should be removed from 1502000-23 in future mod | Dave Strickland
| Backflow Devices - RP 1.5"- Westside of bldg. | MYP-1613-BFP-04 | MAYPOR-1613 |  |  | BREAKDOWN |  | BREAKDOWN | Attached to irrigation system no longer in use/abandoned in place | [14 empty] | Should be removed from 1502000-23 in future mod | Dave Strickland
| Fire Alarm - Navy Lodge (Annunciator) | A125260 | MAYPOR-1980 |  |  | BREAKDOWN |  | BREAKDOWN | Panel has been removed. All zones moved to the Kingfisher | [14 empty] | Should be removed from 1502000-17 in future mod | Dave Strickland
| Aboveground Tank - Bldg. 1587 - Fuel Oil, Heating, Tank 2287, 4000 Gallons (Zone 1) | A117489 | MAYPOR-1587 |  |  | BREAKDOWN |  | BREAKDOWN | Tank emptied and closed/abandoned in place | [14 empty] | Should be removed from 1502000-25 in future mod | Dave Strickland
| Backflow Devices 1"-RP - South Of Building At Fence, Tag #183 | A117626 | MAYFISC-38 |  |  | BREAKDOWN |  | BREAKDOWN | Abandoned, no water supply to device
| Backflow Devices 1"-RP - West Side Of Building, Tag #200 | A117625 | MAYFISC-25 |  |  | BREAKDOWN |  | BREAKDOWN | MAYFISC-25 demolished and replaced with MAYFISC-2669, backflow removed
| Aboveground Tank - Oily Waste Water - 1442-3, 303,453 Gallons (Zone 4) | A125012 | MAYPOR-1442 |  |  | BREAKDOWN |  | BREAKDOWN | Tank is empty and no longer used.
| Underground Tank - Bldg. 1585 - Fuel Oil, Heating, N1585, 5000 Gallons (Zone 1) | A117487 | MAYPOR-1585 |  |  | BREAKDOWN |  |  | Tank is empty and no longer used.
| Underground Tank - Bldg. 1586 - Fuel Oil, Heating, N1586, 5000 Gallons (Zone 1) | A117488 | MAYPOR-1586 |  |  | BREAKDOWN |  |  | Tank is empty and no longer used.
| Aboveground Tank - Bldg. 191 - Fuel Oil, Heating - Tank N191B, 350 Gallon (Zone 1) | A117457 | MAYPOR-191 |  |  | BREAKDOWN |  |  | Tank is empty and no longer used.
| Aboveground Tank - Bldg. 234 - Used Oil - Tank N234C, 560 Gallons (Zone 2) | A117496 | MAYPOR-234 |  |  | BREAKDOWN |  |  | This tank has been closed.
| Aboveground Tank - Bldg. 25 (Zone 2) - Used Oil - Tank 25, 500 Gallon | A117493 | MAYPOR-25 |  |  | BREAKDOWN |  |  | This tank has been closed.
| Aboveground Tank - Bldg. 298 - Fuel Oil, Heating, N298, 1000 Gallons (Zone 1) | A117462 | MAYPOR-25 |  |  | BREAKDOWN |  |  | Tank is empty and no longer used.
| Underground Tank - Bldg. 338 - Fuel Oil, Heating, 338A, 5000 Gallons (Zone 1) | A117463 | MAYPOR-338 |  |  | BREAKDOWN |  |  | Tank is empty and no longer used.
| Backflow Devices -DCVA 2"- West side of bldg., Tag # 393 | A124785 | MAYPOR-1316 |  |  | BREAKDOWN |  |  | Removed and capped off
| Backflow Devices -DCVA 1.5"- East side of Mayport rd, north of bldg. 1962, Device #725 | A124988 | MAYPOR-GROUNDS |  |  | BREAKDOWN |  |  | Removed after a tree fell on the guard shack and the station was removed. Also listed on 1502000-22 at facility #1962.
| Underground Tank - Bldg. 1613 - Used Oil - N1863 1000 Gal (Zone 4) | A117507 | MAYPOR-1613 |  |  | BREAKDOWN |  |  | Tank removed and not replaced
| Valve #1021 Montreal St. North of Assisi Lane South valve 8" | A124588 | MAYPOR-WTR-VLV |  |  | BREAKDOWN |  |  | Inoperable
| Valve #1022 Montreal St. North of Assisi Lane East valve 8" | A124589 | MAYPOR-WTR-VLV |  |  | BREAKDOWN |  |  | Inoperable

## Dropdown lists (hidden)
dropdown menu lists: | Site | Utility | IDIQ type | Action menu | Status Menu | Party | Priority | Jacobs POC
| HVAC Mayport | Electrical | O&A ROM | Jacobs | Planning | Jacobs | 1 | John Armstrong
| Electrical Mayport | Port Ops | RFP | Government | In Scoping -Ops | Subcontractor | 2 | Joe Keeler
| Mech Mayport | High Voltage | O&A RFP |  | In Sub-Contracts |  |  | Rae Hosler
| Carp Mayport | Steam | CAT-1 |  | RFI's to Gov't | TBD | 3 | Alex Reyes
| Plumbing Mayport | Water | CAT-2 |  | Proposal under Review by Jacobs MGT | Jacobs & Sub |  | IDIQ Team
| Painting Mayport | Waste Water | CAT-3 | N/A | Proposal Preparation |  |  | Jarrad Hampton
| Combined Shops Mayport | Enviro | CAT-4 |  | Submitted |  |  | Nolan Green
| Facilities | Mechanic |  |  | RFI's from Gov't |  |  | Cheryl Miller
| Misc Utility | Misc Utility
| Pool | OWWO |  |  | Revalidation |  |  | MBOS PM
| Piers | Various | RFP Storm |  | Execution |  |  | Gene T
| HVAC Controls | Misc Utility | TO |  | Complete |  |  | Colette Snelling
| Environmental |  | REA |  | Waiting Material |  |  | Mark Killmer
| Fire & Safety |  | ER |  | Hold |  |  | Accounting
| Misc Utility |  | INT |  | Cancelled
| Fuel Farm |  | PM-CM |  | Finished
|  |  | IN-KIND |  | Rework
|  |  | BREAKDOWN |  | Invoiced |  | Gov't Review
|  |  | ROM |  | Ready for Invoice |  |  |  | .
Pending Invoice Approval
|  |  | Outside Contract Direct Pay |  | Waiting Funding
On the Shelf
Invoice Rejected
Breakdown
Template row
Declined/ Canceled