## Maxwell AFB Dining Hall Renovat
TITLE: |  |  | Repair Dining Facility, Building 668 | [6 empty] | SUBMITTAL REGISTER
JOB NAME: |  |  | MAXWELLAFB
LOCATION: |  |  | Maxwell AFB, Alabama
CONTRACT NO: |  |  | MAFB-PNQS-09-4491
CONTRACTOR:
[7 empty] | CONTRACTOR SCHEDULE DATES |  |  |  | APPROVING AUTHORITY
Line | Transmittal # | Specification Section | SD # | Submittal Description | Item Submitted | Paragraph # | Submit | Approval Needed By | Material Needed By | Date FWD to APPR / Auth Date RCD From CONTR | Date FWD To Other Revwr | Date RCD From Other Reviewer | Action Code | Date Of Action | Mailed To CONTR/ Date RCD From APPR Authority | Remarks
1 |  | 01 00 00.10 |  | Preconstruction Submittals | AF Form 3000 - Materials Submissions Report | 7.02
2 |  | 01 00 01.10 |  | Preconstruction Submittals | Contractor's Hazardous Materials Questionnaire | 2.6
3 |  | 01 00 01.10 |  | Preconstruction Submittals | Contractor's Environmental Entry Form | 2.6
4 |  | 01 00 01.10 |  | Test Reports | Recycling and Landfill Report | 3.5.1 | [9 empty] | Monthly with Weight Certificates (Item 8)
5 |  | 01 00 01.10 |  | Test Reports | Installation Certification for Clean Construction Debris To Be Removed From the Construction Project Site | 3.5.4
6 |  | 01 14 00 | 1 | Preconstruction Submittals | List of Contact Personnel | 1.4.1.1
7 |  | 01 20 00 | 1 | Preconstruction Submittals | AF Form 3064 Progress Schedule
8 |  | 01 20 00 | 3 | Product Data | Weight Certificates
9 |  | 01 30 00 | 1 | Preconstruction Submittals | View Location Map | 1.4
10 |  | 01 30 00 | 1 | Preconstruction Submittals | Progress and Completion Pictures | 1.5
11 |  | 01 30 00 | 4 | Samples | Color Boards | 1.3
12 |  | 01 33 00 | 1 | Preconstruction Submittals | Submittal Register | 1.2.1
13 |  | 01 33 00 | 1 | Preconstruction Submittals | Submittal Register | 1.8
14 |  | 01 35 33 | 1 | Preconstruction Submittals | Solid Waste Management Permit | 1.1
15 |  | 01 35 33 | 6 | Test Reports | Monthly Solid Waste Disposal Report | 1.10.1
16 |  | 01 35 33 | 11 | Closeout Submittals | Solid Waste Management Permit | 1.1
17 |  | 01 45 00.10 20 | 1 | Preconstruction Submittals | QC Plan | 1.5
18 |  | 01 50 00 | 1 | Preconstruction Submittals | Construction Site Plan | 1.3
19 |  | 01 50 00 | 1 | Preconstruction Submittals | Contractor Computer Cybersecurity Compliance Statements | 1.6.1.4
20 |  | 01 50 00 | 1 | Preconstruction Submittals | Contractor Temporary Network Cybersecurity Compliance Statements | 1.6.6
21 |  | 01 50 00 | 6 | Test Reports | Backflow Preventer Tests | 3.3
22 |  | 01 50 00 | 7 | Certificates | Backflow Tester | 1.4.1
23 |  | 01 50 00 | 7 | Certificates | Backflow Preventers | 1.4
24 |  | 01 74 19 | 1 | Preconstruction Submittals | Construction Waste Management Plan | 1.6
25 |  | 01 74 19 | 6 | Test Reports | Quarterly Reports | 1.8.2
26 |  | 01 74 19 | 11 | Closeout Submittals | Final Construction Waste Diversion Report | 1.9
27 |  | 01 78 23 | 10 | Operation and Maintenance Data | Training Plan | 3.1.1
28 |  | 01 78 23 | 10 | Operation and Maintenance Data | Training Outline | 3.1.3
29 |  | 01 78 23 | 10 | Operation and Maintenance Data | Training Content | 3.1.2
30 |  | 01 78 23 | 11 | Closeout Submittals | Training Video Recording | 3.1.4
31 |  | 01 78 23 | 11 | Closeout Submittals | Validation of Training Completion | 3.1.6
32 |  | 02 41 00 | 2 | Shop Drawings | Existing Conditions | 1.9
33 |  | 02 41 00 | 7 | Certificates | Notification | 1.6
34 |  | 02 42 91 | 1 | Preconstruction Submittals | Work Plan | 1.2
35 |  | 02 61 13 | 1 | Preconstruction Submittals | Work Plan | 1.3
36 |  | 02 61 13 | 2 | Shop Drawings | Surveys | 3.1
37 |  | 02 61 13 | 6 | Test Reports | Compaction | 3.9.2
38 |  | 02 61 13 | 6 | Test Reports | Closure Report | 3.11
39 |  | 02 82 00 | 3 | Product Data | Amended Water | 1.2.3
40 |  | 02 82 00 | 3 | Product Data | Safety Data Sheets (SDS) for All Materials | 1.3.9
41 |  | 02 82 00 | 3 | Product Data | Respirators | 3.1.2.1
42 |  | 02 82 00 | 3 | Product Data | Local Exhaust Equipment | 3.1.7
43 |  | 02 82 00 | 3 | Product Data | Pressure Differential Automatic Recording Instrument | 3.1.7
44 |  | 02 82 00 | 3 | Product Data | Vacuums | 3.1.8
45 |  | 02 82 00 | 6 | Test Reports | Air Sampling Results | 1.5.6
46 |  | 02 82 00 | 6 | Test Reports | Pressure Differential Recordings for Local Exhaust System | 1.5.7
47 |  | 02 82 00 | 6 | Test Reports | Clearance Sampling | 3.2.13.4
48 |  | 02 82 00 | 6 | Test Reports | Asbestos Disposal Quantity Report | 3.3.3.2
49 |  | 02 82 00 | 7 | Certificates | Employee Training | 1.3.4
50 |  | 02 82 00 | 7 | Certificates | Notifications | 1.3.5
51 |  | 02 82 00 | 7 | Certificates | Respiratory Protection Program | 1.3.7
52 |  | 02 82 00 | 7 | Certificates | Asbestos Hazard Abatement Plan | 1.3.10
53 |  | 02 82 00 | 7 | Certificates | Testing Laboratory | 1.3.11
54 |  | 02 82 00 | 7 | Certificates | Landfill Approval | 1.3.12
55 |  | 02 82 00 | 7 | Certificates | Delivery Tickets | 1.3.12
56 |  | 02 82 00 | 7 | Certificates | Waste Shipment Records | 1.3.12
57 |  | 02 82 00 | 7 | Certificates | Transporter Certification | 1.3.13
58 |  | 02 82 00 | 7 | Certificates | Medical Certification | 1.3.14
59 |  | 02 82 00 | 7 | Certificates | Private Qualified Person Documentation | 1.5.1
60 |  | 02 82 00 | 7 | Certificates | Designated Competent Person | 1.5.2
61 |  | 02 82 00 | 7 | Certificates | Worker's License | 1.5.3
62 |  | 02 82 00 | 7 | Certificates | Contractor's License | 1.5.4
63 |  | 02 82 00 | 7 | Certificates | Federal, State or Local Citations on Previous Projects | 1.5.10
64 |  | 02 82 00 | 7 | Certificates | Equipment Used to Contain Airborne Asbestos Fibers | 3.1
65 |  | 02 82 00 | 7 | Certificates | Water Filtration Equipment | 3.1.3.3
66 |  | 02 82 00 | 7 | Certificates | Vacuums | 3.1.8
67 |  | 02 82 00 | 7 | Certificates | Ventilation Systems | 3.1.8
68 |  | 02 82 00 | 7 | Certificates | Glovebags | 3.1.10
69 |  | 02 82 00 | 11 | Closeout Submittals | Permits and Licenses | 1.3.5
70 |  | 02 82 00 | 11 | Closeout Submittals | Notifications | 1.3.5
71 |  | 02 82 00 | 11 | Closeout Submittals | Respirator Program Records | 1.3.7.1
72 |  | 02 82 00 | 11 | Closeout Submittals | Protective Clothing Decontamination Quality Control Records | 1.5.8
73 |  | 02 82 00 | 11 | Closeout Submittals | Protective Clothing Decontamination Facility Notification | 1.5.9
74 |  | 02 82 00 | 11 | Closeout Submittals | Rental Equipment | 1.7.1
75 |  | 02 82 00 | 11 | Closeout Submittals | Air Sampling Analytical Results | 3.2.13.3
76 |  | 02 82 00 | 11 | Closeout Submittals | Daily Report Log | 3.2.13.3
77 |  | 02 82 00 | 11 | Closeout Submittals | Daily Worker Sign-In/Out Sheets | 3.2.13.3
78 |  | 02 82 00 | 11 | Closeout Submittals | Waste Manifest | 3.2.13.3
79 |  | 02 82 00 | 11 | Closeout Submittals | Safe State Certificates | 3.2.13.3
80 |  | 03 30 00 | 1 | Preconstruction Submittals | Concrete Curing Plan | 1.6.3.1
81 |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Plan | 1.6.6
82 |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Personnel Certifications | 1.6.7
83 |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Organizational Chart | 1.6.7
84 |  | 03 30 00 | 1 | Preconstruction Submittals | Laboratory Accreditation | 1.7
85 |  | 03 30 00 | 1 | Preconstruction Submittals | Form Removal Schedule | 1.6.2.1
86 |  | 03 30 00 | 1 | Preconstruction Submittals | Maturity Method Data | 3.3.9
87 |  | 03 30 00 | 2 | Shop Drawings | Formwork | 1.6.2.1
88 |  | 03 30 00 | 2 | Shop Drawings | Reinforcing Steel | 1.6.2.2
89 |  | 03 30 00 | 3 | Product Data | Joint Filler | 2.4.4
90 |  | 03 30 00 | 3 | Product Data | Formwork Materials | 2.1
91 |  | 03 30 00 | 3 | Product Data | Cementitious Materials | 2.3.1
92 |  | 03 30 00 | 3 | Product Data | Vapor Barrier | 2.4.5
93 |  | 03 30 00 | 3 | Product Data | Concrete Curing Materials | 2.4.1
94 |  | 03 30 00 | 3 | Product Data | Reinforcement | 2.6
95 |  | 03 30 00 | 3 | Product Data | Liquid Chemical Floor Hardeners and Sealers | 2.4.3.1
96 |  | 03 30 00 | 3 | Product Data | Admixtures | 2.3.4
97 |  | 03 30 00 | 3 | Product Data | Local/Regional Materials | 1.9.1
98 |  | 03 30 00 | 3 | Product Data | Biodegradable Form Release Agent | 2.2.2
99 |  | 03 30 00 | 3 | Product Data | Pumping Concrete | 1.6.3.2
100 |  | 03 30 00 | 3 | Product Data | Finishing Plan | 1.6.3.3
101 |  | 03 30 00 | 3 | Product Data | Nonshrink Grout | 2.4.2
102 |  | 03 30 00 | 5 | Design Data | Concrete Mix Design | 1.6.1.1
103 |  | 03 30 00 | 6 | Test Reports | Concrete Mix Design | 1.6.1.1
104 |  | 03 30 00 | 6 | Test Reports | Slag Cement | 1.6.4.1
105 |  | 03 30 00 | 6 | Test Reports | Compressive Strength Tests | 3.13.2.3
106 |  | 03 30 00 | 6 | Test Reports | Air Content | 3.13.2.4
107 |  | 03 30 00 | 6 | Test Reports | Slump Tests | 3.13.2.1
108 |  | 03 30 00 | 6 | Test Reports | Water | 2.3.2
109 |  | 03 30 00 | 7 | Certificates | Reinforcing Bars | 2.6.1
110 |  | 03 30 00 | 7 | Certificates | Welder Qualifications | 1.1
111 |  | 03 30 00 | 7 | Certificates | VOC Content for Form Release Agents, Curing Compounds, and Concrete Penetrating Sealers | 1.6.3.4
112 |  | 03 30 00 | 7 | Certificates | Safety Data Sheets | 1.6.3.5
113 |  | 03 30 00 | 7 | Certificates | Forest Stewardship Council (FSC) Certification | 1.9.2
114 |  | 03 30 00 | 7 | Certificates | Field Testing Technician and Testing Agency | 1.6.7.2
115 |  | 03 30 00 | 8 | Manufacturer's Instructions | Liquid Chemical Floor Hardeners and Sealers | 2.4.3.1
116 |  | 03 30 00 | 8 | Manufacturer's Instructions | Curing Compound | 2.4.1
117 |  | 04 20 00 | 2 | Shop Drawings | Cut CMU | 3.3.2.1
118 |  | 04 20 00 | 2 | Shop Drawings | Reinforcement Detail Drawings | 3.4.1.1
119 |  | 04 20 00 | 3 | Product Data | Hot Weather Procedures | 1.5.1
120 |  | 04 20 00 | 3 | Product Data | Cold Weather Procedures | 1.5.2
121 |  | 04 20 00 | 4 | Samples | Mock-Up Panel | 1.3.1.1
122 |  | 04 20 00 | 4 | Samples | Concrete Masonry Units (CMU) | 2.1.2
123 |  | 04 20 00 | 4 | Samples | Concrete Brick | 2.1.2.3
124 |  | 04 20 00 | 4 | Samples | Admixtures for Masonry Mortar | 2.3.1.1
125 |  | 04 20 00 | 4 | Samples | Joint Reinforcement | 2.5.2
126 |  | 04 20 00 | 5 | Design Data | Bracing Calculations | 3.2.4
127 |  | 04 20 00 | 7 | Certificates | Concrete Masonry Units (CMU) | 2.1.2
128 |  | 04 20 00 | 7 | Certificates | Concrete Brick | 2.1.2.3
129 |  | 04 20 00 | 7 | Certificates | Admixtures for Masonry Mortar | 2.3.1.1
130 |  | 04 20 00 | 7 | Certificates | Admixtures for Grout | 2.3.2.2
131 |  | 04 20 00 | 7 | Certificates | Joint Reinforcement | 2.5.2
132 |  | 04 20 00 | 8 | Manufacturer's Instructions | Admixtures for Masonry Mortar | 2.3.1.1
133 |  | 04 20 00 | 8 | Manufacturer's Instructions | Admixtures for Grout | 2.3.2.2
134 |  | 04 20 00 | 10 | Operation and Maintenance Data | Take-Back Program | 3.8
135 |  | 05 50 13 | 2 | Shop Drawings | Angles and Plates | 2.5
136 |  | 05 50 13 | 2 | Shop Drawings | Roof Hatches | 2.6
137 |  | 05 50 13 | 2 | Shop Drawings | Ladders | 2.7
138 |  | 05 50 13 | 3 | Product Data | Roof Hatches | 2.6
139 |  | 05 50 13 | 3 | Product Data | Downspout Terminations | 2.4
140 |  | 05 50 13 | 3 | Product Data | Recycled Content | 2.1
141 |  | 06 10 00 | 2 | Shop Drawings | Modifications of Structural Members | 1.9.2
142 |  | 06 10 00 | 2 | Shop Drawings | Nailing Strips | 2.2.2
143 |  | 06 10 00 | 2 | Shop Drawings | Fabricated Structural Members | 1.9.1
144 |  | 06 10 00 | 2 | Shop Drawings | Prefabricated Wood Trusses | 2.4.2
145 |  | 06 10 00 | 3 | Product Data | Fire-retardant Treatment | 1.8
146 |  | 06 10 00 | 3 | Product Data | Adhesives | 2.4.4
147 |  | 06 10 00 | 5 | Design Data | Modifications of Structural Members | 1.9.2
148 |  | 06 10 00 | 6 | Test Reports | Preservative-treated | 1.4.3
149 |  | 06 10 00 | 7 | Certificates | Preservative Treatment | 1.7
150 |  | 06 20 00 | 2 | Shop Drawings | Detail Drawings Indicating All Wood Assemblies | 1.3
151 |  | 06 20 00 | 2 | Shop Drawings | Cabinet Work | 2.3
152 |  | 06 20 00 | 3 | Product Data | Wood Products | 2.1
153 |  | 06 20 00 | 3 | Product Data | Countertops | 2.4
154 |  | 06 20 00 | 3 | Product Data | Treated Wood Products | 1.4
155 |  | 06 20 00 | 3 | Product Data | Fascias and Trim | 2.2
156 |  | 06 20 00 | 3 | Product Data | Hardware and Accessories | 2.7
157 |  | 06 20 00 | 3 | Product Data | Plastic Laminates | 2.3.1
158 |  | 06 20 00 | 3 | Product Data | Quartz Agglomerate Material | 2.4.2
159 |  | 06 20 00 | 3 | Product Data | Quartz Counter Tops | 2.8.4.1
160 |  | 06 20 00 | 4 | Samples | Plastic Laminates | 2.3.1
161 |  | 06 20 00 | 4 | Samples | Samples | 1.5
162 |  | 06 20 00 | 7 | Certificates | Certificates of Grade | 1.7.1.1
163 |  | 06 20 00 | 7 | Certificates | Indoor Air Quality for Non-aerosol Adhesives | 2.8.3
164 |  | 06 20 00 | 7 | Certificates | Indoor Air Quality for Aerosol Adhesives | 2.8.3
165 |  | 06 20 00 | 7 | Certificates | Indoor Air Quality For Solid Surface Fabrication Products | 2.4.2
166 |  | 07 14 00 | 3 | Product Data | Protection Board | 2.3
167 |  | 07 14 00 | 3 | Product Data | Polymer-Modified Cement Waterproofing | 2.1
168 |  | 07 14 00 | 6 | Test Reports | Moisture Meter | 3.5.1
169 |  | 07 14 00 | 11 | Closeout Submittals | Warranty | 1.6
170 |  | 07 21 00 | 3 | Product Data | Blanket Insulation | 2.1
171 |  | 07 21 00 | 3 | Product Data | Recycled Content for Insulation Materials | 2.1.2
172 |  | 07 21 00 | 3 | Product Data | Pressure Sensitive Tape | 2.4
173 |  | 07 21 00 | 3 | Product Data | Accessories | 2.5
174 |  | 07 21 00 | 3 | Product Data | Insulation Fasteners | 2.6
175 |  | 07 21 00 | 3 | Product Data | Semi-Rigid Board Insulation | 2.2
176 |  | 07 21 00 | 7 | Certificates | Indoor Air Quality for Adhesives | 2.5.1
177 |  | 07 21 00 | 8 | Manufacturer's Instructions | Insulation | 3.3.1
178 |  | 07 27 26 | 1 | Preconstruction Submittals | Qualifications of Manufacturer | 1.8.1
179 |  | 07 27 26 | 1 | Preconstruction Submittals | Qualifications of Installer | 1.8.2
180 |  | 07 27 26 | 2 | Shop Drawings | Fluid-Applied Membrane Air Barrier | 1.4
181 |  | 07 27 26 | 3 | Product Data | Fluid-Applied Membrane Air Barrier | 1.4
182 |  | 07 27 26 | 3 | Product Data | Transition Membrane | 2.3
183 |  | 07 27 26 | 3 | Product Data | Primers, Adhesives, and Mastics | 2.2
184 |  | 07 27 26 | 3 | Product Data | Safety Data Sheets | 1.4.3
185 |  | 07 27 26 | 4 | Samples | Mockup | 1.4.4
186 |  | 07 27 26 | 6 | Test Reports | Capillary Moisture Test | 1.6
187 |  | 07 27 26 | 6 | Test Reports | Field Peel Adhesion Test | 1.4.5
188 |  | 07 27 26 | 6 | Test Reports | Site Inspections | 3.4.1
189 |  | 07 27 26 | 7 | Certificates | Fluid-Applied Membrane Air Barrier | 1.4
190 |  | 07 27 26 | 7 | Certificates | Transition Membrane | 2.3
191 |  | 07 27 26 | 8 | Manufacturer's Instructions | Fluid-Applied Membrane Air Barrier | 1.4
192 |  | 07 27 26 | 8 | Manufacturer's Instructions | Transition Membrane | 2.3
193 |  | 07 27 26 | 8 | Manufacturer's Instructions | Primers, Adhesives, and Mastics | 2.2
194 |  | 07 41 13 | 2 | Shop Drawings | Metal Tile Roofing System | 1.7.2
195 |  | 07 41 13 | 3 | Product Data | Metal Tile Roofing System | 1.7.2
196 |  | 07 41 13 | 3 | Product Data | Underlayment Membrane | 2.2
197 |  | 07 41 13 | 3 | Product Data | Flexible Hip and Ridge Flashing | 2.2.1
198 |  | 07 41 13 | 3 | Product Data | Sealant | 2.4
199 |  | 07 41 13 | 3 | Product Data | Metal Roof Tiles | 2.1.2
200 |  | 07 41 13 | 4 | Samples | Metal Roof Tiles | 2.1.2
201 |  | 07 41 13 | 6 | Test Reports | Self-Adhering Membrane Underlayment | 2.2.2
202 |  | 07 41 13 | 7 | Certificates | Qualifications | 1.7.1
203 |  | 07 41 13 | 8 | Manufacturer's Instructions | Installation | 3.3
204 |  | 07 54 19 | 2 | Shop Drawings | Detail Drawings | 1.6
205 |  | 07 54 19 | 2 | Shop Drawings | Roof Plan | 1.6
206 |  | 07 54 19 | 3 | Product Data | TPO Roofing Membrane | 3.2.2
207 |  | 07 54 19 | 3 | Product Data | Energy Star Label for roof membrane | 2.1.2
208 |  | 07 54 19 | 3 | Product Data | Bonding Adhesive | 2.1.3
209 |  | 07 54 19 | 3 | Product Data | Flashing | 1.5.4
210 |  | 07 54 19 | 3 | Product Data | Flashing | 3.2.2.2
211 |  | 07 54 19 | 3 | Product Data | Membrane Fasteners and Plates | 2.1.7
212 |  | 07 54 19 | 3 | Product Data | Roof Insulation | 2.1.8
213 |  | 07 54 19 | 3 | Product Data | Water Cutoffs | 3.6.1
214 |  | 07 54 19 | 3 | Product Data | Information Card | 2.1.1
215 |  | 07 54 19 | 5 | Design Data | Wind Uplift Resistance | 1.3.2
216 |  | 07 54 19 | 7 | Certificates | Qualification of Manufacturer | 1.5.1
217 |  | 07 54 19 | 7 | Certificates | Qualifications of Applicator | 1.5.2
218 |  | 07 54 19 | 7 | Certificates | Qualification of Engineer of Record | 1.5.3
219 |  | 07 54 19 | 7 | Certificates | Wind Uplift Resistance | 1.3.2
220 |  | 07 54 19 | 7 | Certificates | Fire Resistance | 1.3.1
221 |  | 07 54 19 | 7 | Certificates | Sample | 1.1
222 |  | 07 54 19 | 8 | Manufacturer's Instructions | Application Method | 3.2
223 |  | 07 54 19 | 8 | Manufacturer's Instructions | Membrane Flashing | 2.1.6
224 |  | 07 54 19 | 8 | Manufacturer's Instructions | Membrane Flashing | 3.3.2
225 |  | 07 54 19 | 8 | Manufacturer's Instructions | Auxiliary Fasteners | 2.1.7.2
226 |  | 07 54 19 | 8 | Manufacturer's Instructions | Cold Weather | 1.8
227 |  | 07 54 19 | 11 | Closeout Submittals | Warranty | 1.1
228 |  | 07 54 19 | 11 | Closeout Submittals | Information Card | 2.1.1
229 |  | 07 54 19 | 11 | Closeout Submittals | Instructions to Government Personnel | 3.9
230 |  | 07 84 00 | 2 | Shop Drawings | Firestopping System | 2.1
231 |  | 07 84 00 | 3 | Product Data | Firestopping Materials | 2.2
232 |  | 07 84 00 | 6 | Test Reports | Inspection | 3.4
233 |  | 07 84 00 | 7 | Certificates | Firestopping Materials | 2.2
234 |  | 07 84 00 | 7 | Certificates | Installer Qualifications | 1.5.1
235 |  | 07 84 00 | 7 | Certificates | Inspector Qualifications | 1.5.2
236 |  | 07 92 00 | 3 | Product Data | Sealants | 2.1
237 |  | 07 92 00 | 3 | Product Data | Primers | 2.2
238 |  | 07 92 00 | 3 | Product Data | Bond Breakers | 2.3
239 |  | 07 92 00 | 3 | Product Data | Backstops | 2.4
240 |  | 07 92 00 | 3 | Product Data | Field Adhesion | 3.1
241 |  | 07 92 00 | 7 | Certificates | Indoor Air Quality For Interior Sealants | 2.1.1
242 |  | 07 92 00 | 7 | Certificates | Indoor Air Quality For Interior Acoustical Sealants | 2.1.4
243 |  | 08 11 13 | 2 | Shop Drawings | Doors | 2.2
244 |  | 08 11 13 | 2 | Shop Drawings | Doors | 2.2
245 |  | 08 11 13 | 2 | Shop Drawings | Frames | 2.8
246 |  | 08 11 13 | 2 | Shop Drawings | Frames | 2.8
247 |  | 08 11 13 | 2 | Shop Drawings | Accessories | 2.6
248 |  | 08 11 13 | 3 | Product Data | Doors | 2.2
249 |  | 08 11 13 | 3 | Product Data | Recycled Content for Steel Door Product | 2.2
250 |  | 08 11 13 | 3 | Product Data | Frames | 2.8
251 |  | 08 11 13 | 3 | Product Data | Recycled Content for Steel Frame Product | 2.8
252 |  | 08 11 13 | 3 | Product Data | Accessories | 2.6
253 |  | 08 14 00 | 2 | Shop Drawings | Doors | 2.1
254 |  | 08 14 00 | 3 | Product Data | Doors | 2.1
255 |  | 08 14 00 | 3 | Product Data | Accessories | 2.2
256 |  | 08 14 00 | 3 | Product Data | Water-resistant Sealer | 2.3.6
257 |  | 08 14 00 | 3 | Product Data | Warranty | 1.4
258 |  | 08 14 00 | 4 | Samples | Doors | 2.1
259 |  | 08 14 00 | 4 | Samples | Door Finish Colors | 2.3.5.3
260 |  | 08 14 00 | 6 | Test Reports | Cycle-Slam | 2.4
261 |  | 08 14 00 | 6 | Test Reports | Hinge Loading Resistance | 2.4
262 |  | 08 14 00 | 11 | Closeout Submittals | Warranty | 1.4
263 |  | 08 31 00 | 2 | Shop Drawings | Access Doors And Panels | 1.3
264 |  | 08 31 00 | 3 | Product Data | Access Doors And Panels | 1.3
265 |  | 08 31 00 | 3 | Product Data | Hardware | 1.3.2
266 |  | 08 31 00 | 3 | Product Data | Accessories | 2.2.7
267 |  | 08 31 00 | 3 | Product Data | Recycled Content | 2.1
268 |  | 08 31 00 | 4 | Samples | Finishes | 2.5
269 |  | 08 41 13 | 1 | Preconstruction Submittals | Sample Warranty | 1.2.1
270 |  | 08 41 13 | 1 | Preconstruction Submittals | List of Product Installations | 1.2.1
271 |  | 08 41 13 | 2 | Shop Drawings | Installation Drawings | 3.3
272 |  | 08 41 13 | 2 | Shop Drawings | Fabrication Drawings | 2.2
273 |  | 08 41 13 | 3 | Product Data | Manufacturer's Catalog Data | 1.2.1
274 |  | 08 41 13 | 3 | Product Data | Finish | 2.2.3
275 |  | 08 41 13 | 3 | Product Data | Recycled Content of Aluminum Material | 2.1.1.2
276 |  | 08 41 13 | 4 | Samples | Finish and Color Samples | 1.2.1
277 |  | 08 41 13 | 6 | Test Reports | Certified Test Reports | 1.2.1
278 |  | 08 41 13 | 6 | Test Reports | Deflection | 3.4.3
279 |  | 08 41 13 | 6 | Test Reports | Air Infiltration | 3.4.1
280 |  | 08 41 13 | 6 | Test Reports | Condensation Resistance and Thermal Transmittance | 3.4.4
281 |  | 08 41 13 | 6 | Test Reports | Water Infiltration | 3.4.5
282 |  | 08 41 13 | 8 | Manufacturer's Instructions | Manufacturer's Instructions | 3.3
283 |  | 08 41 13 | 11 | Closeout Submittals | Manufacturer's Product Warranty | 3.6
284 |  | 08 51 13 | 2 | Shop Drawings | Windows | 2.1
285 |  | 08 51 13 | 2 | Shop Drawings | Fabrication Drawings | 1.6
286 |  | 08 51 13 | 3 | Product Data | Windows | 2.1
287 |  | 08 51 13 | 3 | Product Data | Fasteners | 2.2.2
288 |  | 08 51 13 | 3 | Product Data | Window Performance | 1.5
289 |  | 08 51 13 | 3 | Product Data | Thermal-Barrier Windows | 2.3
290 |  | 08 51 13 | 3 | Product Data | Mullions | 2.4
291 |  | 08 51 13 | 3 | Product Data | Accessories | 2.2.7
292 |  | 08 51 13 | 3 | Product Data | Adhesives | 2.2.3
293 |  | 08 51 13 | 4 | Samples | Finish Sample | 1.3.3.1
294 |  | 08 51 13 | 4 | Samples | Window Sample | 1.3.3.2
295 |  | 08 51 13 | 5 | Design Data | Structural Calculations for Deflection | 2.1
296 |  | 08 51 13 | 6 | Test Reports | Minimum Condensation Resistance Factor | 1.3.4
297 |  | 08 51 13 | 10 | Operation and Maintenance Data | Windows | 2.1
298 |  | 08 71 00 | 2 | Shop Drawings | Manufacturer's Detail Drawings | 1.3
299 |  | 08 71 00 | 2 | Shop Drawings | Verification of Existing Conditions | 1.3
300 |  | 08 71 00 | 2 | Shop Drawings | Hardware Schedule | 1.5
301 |  | 08 71 00 | 2 | Shop Drawings | Keying System | 2.3.8
302 |  | 08 71 00 | 3 | Product Data | Hardware Items | 2.3
303 |  | 08 71 00 | 8 | Manufacturer's Instructions | Installation | 3.1
304 |  | 08 71 00 | 10 | Operation and Maintenance Data | Hardware Schedule | 1.5
305 |  | 08 71 00 | 11 | Closeout Submittals | Key Bitting | 1.6.1
306 |  | 08 81 00 | 3 | Product Data | Insulating Glass | 2.3
307 |  | 08 81 00 | 3 | Product Data | Glazing Accessories | 1.3
308 |  | 08 81 00 | 3 | Product Data | Sealants | 2.4.3.1
309 |  | 08 81 00 | 4 | Samples | Insulating Glass | 2.3
310 |  | 08 81 00 | 4 | Samples | Glazing Compound | 2.4.2
311 |  | 08 81 00 | 4 | Samples | Tape | 2.4.5
312 |  | 08 81 00 | 4 | Samples | Sealing Tapes | 2.4.5
313 |  | 08 81 00 | 7 | Certificates | Insulating Glass | 2.3
314 |  | 08 81 00 | 8 | Manufacturer's Instructions | Setting and Sealing Materials | 2.4
315 |  | 08 81 00 | 8 | Manufacturer's Instructions | Glass Setting | 3.2
316 |  | 08 81 00 | 11 | Closeout Submittals | Insulated Glass Units | 1.7.1
317 |  | 08 81 00 | 11 | Closeout Submittals | Monolithic Reflective Glass | 1.7.2
318 |  | 08 91 00 | 2 | Shop Drawings | Wall Louvers | 1.4
319 |  | 08 91 00 | 3 | Product Data | Metal Wall Louvers | 2.2
320 |  | 08 91 00 | 4 | Samples | Wall Louver Samples | 1.5
321 |  | 09 22 00 | 2 | Shop Drawings | Metal Support Systems | 2.1
322 |  | 09 22 00 | 3 | Product Data | Metal Support Systems | 2.1
323 |  | 09 22 00 | 3 | Product Data | Recycled Content for Metal Support Systems | 2.1
324 |  | 09 24 23 | 2 | Shop Drawings | Lath | 3.4
325 |  | 09 24 23 | 3 | Product Data | Proportions and Mixing | 3.6
326 |  | 09 24 23 | 3 | Product Data | Acrylic Stucco System | 2.1.1
327 |  | 09 24 23 | 3 | Product Data | Weather Barrier | 2.9
328 |  | 09 24 23 | 4 | Samples | Colored Stucco Finish Coat | 2.4
329 |  | 09 24 23 | 4 | Samples | Sample Panel | 1.3
330 |  | 09 24 23 | 7 | Certificates | Recycled Content For Metal Lath | 2.1
331 |  | 09 29 00 | 3 | Product Data | Glass Mat Water-Resistant Gypsum Tile Backing Board | 2.1.2
332 |  | 09 29 00 | 3 | Product Data | Glass Mat Covered or Reinforced Gypsum Sheathing | 2.1.3
333 |  | 09 29 00 | 3 | Product Data | Glass Mat Covered or Reinforced Gypsum Sheathing Sealant | 2.1.3.1
334 |  | 09 29 00 | 3 | Product Data | Accessories | 2.1.6
335 |  | 09 29 00 | 3 | Product Data | Gypsum Board | 2.1.1
336 |  | 09 29 00 | 3 | Product Data | VOC Content of Joint Compound | 2.1.4
337 |  | 09 29 00 | 6 | Test Reports | ASTM E90 Factory Test Report | 3.5
338 |  | 09 29 00 | 7 | Certificates | Asbestos Free Materials | 2.1
339 |  | 09 29 00 | 7 | Certificates | Indoor Air Quality for Gypsum Board | 2.1.1
340 |  | 09 30 10 | 2 | Shop Drawings | Detail Drawings | 3.2
341 |  | 09 30 10 | 3 | Product Data | Porcelain Tile | 2.1.1
342 |  | 09 30 10 | 3 | Product Data | Porcelain Tile | 2.1.2
343 |  | 09 30 10 | 3 | Product Data | Recycled Content for Porcelain Tile | 2.1.1
344 |  | 09 30 10 | 3 | Product Data | Transition Strips | 2.1
345 |  | 09 30 10 | 3 | Product Data | Transition Strips | 2.5.1
346 |  | 09 30 10 | 3 | Product Data | Mortar, Grout, and Adhesive | 2.3
347 |  | 09 30 10 | 3 | Product Data | Cementitious Backer Units | 2.4.1
348 |  | 09 30 10 | 3 | Product Data | Waterproof Membrane | 2.6
349 |  | 09 30 10 | 3 | Product Data | Crack Isolation Membrane | 2.7
350 |  | 09 30 10 | 4 | Samples | Tile | 2.1
351 |  | 09 30 10 | 4 | Samples | Accessories | 2.1
352 |  | 09 30 10 | 4 | Samples | Transition Strips | 2.1
353 |  | 09 30 10 | 4 | Samples | Transition Strips | 2.5.1
354 |  | 09 30 10 | 4 | Samples | Grout | 2.3.2
355 |  | 09 30 10 | 7 | Certificates | Indoor Air Quality for Sealants | 2.3.3
356 |  | 09 30 10 | 7 | Certificates | Water Absorption Rates | 1.3.2
357 |  | 09 30 10 | 8 | Manufacturer's Instructions | Manufacturer's Approved Cleaning Instructions | 3.8
358 |  | 09 30 10 | 10 | Operation and Maintenance Data | Porcelain Tile | 2.1.1
359 |  | 09 30 10 | 10 | Operation and Maintenance Data | Porcelain Tile | 2.1.2
360 |  | 09 30 10 | 10 | Operation and Maintenance Data | Transition Strips | 2.1
361 |  | 09 30 10 | 10 | Operation and Maintenance Data | Transition Strips | 2.5.1
362 |  | 09 51 00 | 2 | Shop Drawings | Drawings | 2.1
363 |  | 09 51 00 | 3 | Product Data | Acoustical Performance | 2.1.1
364 |  | 09 51 00 | 4 | Samples | Acoustical Units | 2.2
365 |  | 09 51 00 | 7 | Certificates | Indoor Air Quality for Adhesives | 2.6
366 |  | 09 51 00 | 7 | Certificates | Indoor Air Quality for Sealants | 2.9
367 |  | 09 65 00 | 2 | Shop Drawings | Resilient Flooring and Accessories | 2.9
368 |  | 09 65 00 | 3 | Product Data | Resilient Flooring and Accessories | 2.9
369 |  | 09 65 00 | 3 | Product Data | Adhesives | 2.4
370 |  | 09 65 00 | 3 | Product Data | Luxury Vinyl Tile | 2.1
371 |  | 09 65 00 | 3 | Product Data | Wall Base | 2.2
372 |  | 09 65 00 | 4 | Samples | Resilient Flooring and Accessories | 2.9
373 |  | 09 65 00 | 6 | Test Reports | Moisture, Alkalinity and Bond Tests | 3.3
374 |  | 09 65 00 | 7 | Certificates | Indoor Air Quality for Adhesives | 2.4
375 |  | 09 65 00 | 8 | Manufacturer's Instructions | Surface Preparation | 3.2
376 |  | 09 65 00 | 8 | Manufacturer's Instructions | Installation | 3.1
377 |  | 09 65 00 | 10 | Operation and Maintenance Data | Resilient Flooring and Accessories | 2.9
378 |  | 09 67 23.13 | 2 | Shop Drawings | Installation Drawings | 2.1
379 |  | 09 67 23.13 | 3 | Product Data | Manufacturer's Catalog Data | 1.2.2
380 |  | 09 67 23.13 | 4 | Samples | Hardboard Mounted Epoxy Flooring | 1.5.3
381 |  | 09 67 23.13 | 4 | Samples | Floor Topping | 3.1.4
382 |  | 09 67 23.13 | 4 | Samples | Mockups | 1.5.1
383 |  | 09 67 23.13 | 5 | Design Data | Design Mix Data | 1.2.3
384 |  | 09 67 23.13 | 7 | Certificates | Listing of Product Installations | 1.5.2
385 |  | 09 67 23.13 | 7 | Certificates | Referenced Standards Certificates | 1.5
386 |  | 09 67 23.13 | 11 | Closeout Submittals | Warranty | 1.6
387 |  | 09 72 00 | 3 | Product Data | Wallcoverings and Accessories | 2.1
388 |  | 09 72 00 | 3 | Product Data | Primer and Adhesive | 2.5
389 |  | 09 72 00 | 3 | Product Data | Recycled Content for wallcovering | 2.3
390 |  | 09 72 00 | 4 | Samples | Wallcoverings and Accessories | 2.1
391 |  | 09 72 00 | 7 | Certificates | Indoor Air Quality | 1.3.1
392 |  | 09 72 00 | 8 | Manufacturer's Instructions | Wallcoverings and Accessories | 2.1
393 |  | 09 72 00 | 10 | Operation and Maintenance Data | Wallcoverings and Accessories | 2.1
394 |  | 09 90 00 | 2 | Shop Drawings | Piping Identification | 3.12
395 |  | 09 90 00 | 3 | Product Data | Coating | 2.1
396 |  | 09 90 00 | 3 | Product Data | Product Data Sheets | 2.1
397 |  | 09 90 00 | 3 | Product Data | Sealant | 3.3.5
398 |  | 09 90 00 | 4 | Samples | Color | 2.2
399 |  | 09 90 00 | 7 | Certificates | Qualification Testing | 1.5.5.2
400 |  | 09 90 00 | 7 | Certificates | Indoor Air Quality for Paints and Primers | 1.5.4
401 |  | 09 90 00 | 8 | Manufacturer's Instructions | Application Instructions | 3.4.1
402 |  | 09 90 00 | 8 | Manufacturer's Instructions | Mixing | 2.1
403 |  | 09 90 00 | 8 | Manufacturer's Instructions | Manufacturer's Safety Data Sheets | 1.7.1
404 |  | 09 90 00 | 10 | Operation and Maintenance Data | Coatings | 2.1
405 |  | 10 14 00.10 | 2 | Shop Drawings | Approved Detail Drawings | 3.1
406 |  | 10 14 00.10 | 3 | Product Data | Installation | 3.1
407 |  | 10 14 00.10 | 3 | Product Data | Exterior Signage | 1.2
408 |  | 10 14 00.10 | 3 | Product Data | Wind Load Requirements | 1.2.1
409 |  | 10 14 00.10 | 4 | Samples | Exterior Signage | 1.2
410 |  | 10 14 00.10 | 10 | Operation and Maintenance Data | Protection and Cleaning | 3.1.2
411 |  | 10 14 00.20 | 2 | Shop Drawings | Detail Drawings | 1.3.2
412 |  | 10 14 00.20 | 3 | Product Data | Room Identification And Directional Signage System | 2.1
413 |  | 10 14 00.20 | 3 | Product Data | Exit Door Tactile Sign | 2.2
414 |  | 10 14 00.20 | 4 | Samples | Interior Signage | 1.3.1
415 |  | 10 14 00.20 | 4 | Samples | Room Identification And Directional Signage System | 2.1
416 |  | 10 14 00.20 | 4 | Samples | Exit Door Tactile Sign | 2.2
417 |  | 10 14 00.20 | 10 | Operation and Maintenance Data | Approved Manufacturer's Instructions | 3.2
418 |  | 10 14 00.20 | 10 | Operation and Maintenance Data | Protection and Cleaning | 3.2.2
419 |  | 10 21 13 | 2 | Shop Drawings | Fabrication Drawings | 2.1
420 |  | 10 21 13 | 2 | Shop Drawings | Installation Drawings | 3.2
421 |  | 10 21 13 | 3 | Product Data | Cleaning and Maintenance Instructions | 2.1
422 |  | 10 21 13 | 3 | Product Data | Colors And Finishes | 2.9
423 |  | 10 21 13 | 3 | Product Data | Anchoring Devices and Fasteners | 2.2.2
424 |  | 10 21 13 | 3 | Product Data | Hardware and Fittings | 2.2.4
425 |  | 10 21 13 | 3 | Product Data | Brackets | 2.2.3
426 |  | 10 21 13 | 3 | Product Data | Door Hardware | 2.2.5
427 |  | 10 21 13 | 3 | Product Data | Pilaster Shoes | 2.7
428 |  | 10 21 13 | 3 | Product Data | Finishes | 2.2.4.2
429 |  | 10 21 13 | 3 | Product Data | Finishes | 2.9.2
430 |  | 10 21 13 | 4 | Samples | Colors and Finishes | 2.9
431 |  | 10 21 13 | 4 | Samples | Hardware and Fittings | 2.2.4
432 |  | 10 21 13 | 4 | Samples | Anchoring Devices and Fasteners | 2.2.2
433 |  | 10 21 13 | 7 | Certificates | Warranty | 1.6
434 |  | 10 28 13 | 2 | Shop Drawings | Product Schedule | 2.1
435 |  | 10 28 13 | 3 | Product Data | Recycled content for stainless steel toilet accessories | 2.1
436 |  | 10 28 13 | 3 | Product Data | Item A5080 | 2.1.3
437 |  | 10 28 13 | 3 | Product Data | Item A5090 | 2.1.4
438 |  | 10 28 13 | 3 | Product Data | Item A5109 | 2.1.5
439 |  | 10 28 13 | 3 | Product Data | Item A5195 | 2.1.6
440 |  | 10 28 13 | 10 | Operation and Maintenance Data | Item A5080 | 2.1.3
441 |  | 10 28 13 | 10 | Operation and Maintenance Data | Item A5090 | 2.1.4
442 |  | 10 28 13 | 10 | Operation and Maintenance Data | Item A5109 | 2.1.5
443 |  | 10 28 13 | 10 | Operation and Maintenance Data | Item A5195 | 2.1.6
444 |  | 10 44 16 | 2 | Shop Drawings | Fire Extinguishers | 2.1.1
445 |  | 10 44 16 | 2 | Shop Drawings | Cabinets | Part 2
446 |  | 10 44 16 | 2 | Shop Drawings | Schedule | 1.5
447 |  | 10 44 16 | 3 | Product Data | Fire Extinguishers | 2.1.1
448 |  | 10 44 16 | 3 | Product Data | Cabinets | Part 2
449 |  | 10 44 16 | 3 | Product Data | Replacement Parts List | 3.2.1
450 |  | 10 44 16 | 4 | Samples | Equipment Samples | 1.3.1
451 |  | 10 44 16 | 7 | Certificates | Fire Extinguishers Certifications | 2.1.1
452 |  | 10 44 16 | 7 | Certificates | Manufacturer's Warranty with Inspection Tag | 1.4
453 |  | 10 51 10 | 2 | Shop Drawings | Types | 2.1
454 |  | 10 51 10 | 2 | Shop Drawings | Location | 1.4
455 |  | 10 51 10 | 2 | Shop Drawings | Installation | 3.1
456 |  | 10 51 10 | 2 | Shop Drawings | Numbering system | 3.2
457 |  | 10 51 10 | 3 | Product Data | Material | 2.2
458 |  | 10 51 10 | 3 | Product Data | Locking Devices | 2.3.1
459 |  | 10 51 10 | 3 | Product Data | Handles | 2.3.3
460 |  | 10 51 10 | 3 | Product Data | components | 2.3
461 |  | 10 51 10 | 3 | Product Data | Assembly | 3.1
462 |  | 10 51 10 | 4 | Samples | Color chips | 1.5.1
463 |  | 11 05 40 | 1 | Preconstruction Submittals | Contractor's Field Verification Data | 1.3
464 |  | 11 05 40 | 1 | Preconstruction Submittals | Manufacturer's Qualifications | 1.6.7
465 |  | 11 05 40 | 2 | Shop Drawings | Detail Drawings | 1.6.7
466 |  | 11 05 40 | 2 | Shop Drawings | Food Service Equipment Schedule | 1.2
467 |  | 11 05 40 | 2 | Shop Drawings | Utilities | 1.5.2
468 |  | 11 05 40 | 2 | Shop Drawings | Utilities | 1.6.7
469 |  | 11 05 40 | 2 | Shop Drawings | Custom Fabricated Equipment | 1.6.7
470 |  | 11 05 40 | 2 | Shop Drawings | Installation Instructions and Diagrams | 1.6.7
471 |  | 11 05 40 | 3 | Product Data | Food Service Equipment | 1.3.1
472 |  | 11 05 40 | 3 | Product Data | Food Preparation Equipment | 1.6.7
473 |  | 11 05 40 | 4 | Samples | Exterior Panel Finish Material | 1.6.7
474 |  | 11 05 40 | 4 | Samples | Interior Panel Finish Material | 1.6.7
475 |  | 11 05 40 | 4 | Samples | Sample Warranty | 1.6.7
476 |  | 11 05 40 | 5 | Design Data | Manufacturer's Descriptive And Technical Literature | 1.6.7
477 |  | 11 05 40 | 6 | Test Reports | Manufacturer's Test Data | 1.6.7
478 |  | 11 05 40 | 6 | Test Reports | Field Test Reports | 3.7.2
479 |  | 11 05 40 | 7 | Certificates | National Sanitation Foundation Standards | 1.6.3
480 |  | 11 05 40 | 7 | Certificates | Underwriters Laboratories Standards | 1.6.6
481 |  | 11 05 40 | 7 | Certificates | Energy Star Labeled | 1.6.2
482 |  | 11 05 40 | 7 | Certificates | Energy Star Labeled | 2.2.6.2
483 |  | 11 05 40 | 7 | Certificates | PL 109-58 Compliant | 1.6.2
484 |  | 11 05 40 | 7 | Certificates | Fabricator/Manufacturer Qualifications | 1.6.1
485 |  | 11 05 40 | 7 | Certificates | Walk-In Refrigeration | 1.5.4
486 |  | 11 05 40 | 7 | Certificates | Preservative-Treated Wood | 1.5.4
487 |  | 11 05 40 | 7 | Certificates | Fire-Retardant Treatment | 1.5.4
488 |  | 11 05 40 | 8 | Manufacturer's Instructions | Manufacturer's Instructions | 1.6.7
489 |  | 11 05 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.5
490 |  | 11 05 40 | 10 | Operation and Maintenance Data | List of Authorized Local Service and Repair Entities | 3.6
491 |  | 11 05 40 | 11 | Closeout Submittals | Manufacturer's Warranty | 3.8
492 |  | 11 05 40 | 11 | Closeout Submittals | Contractor's Warranty for Installation | 3.9
493 |  | 11 06 40.13 | 2 | Shop Drawings | Schedule | 2.8.2
494 |  | 21 13 00.00 40 | 1 | Preconstruction Submittals | Record of Existing Conditions | 1.2
495 |  | 21 13 00.00 40 | 2 | Shop Drawings | Supporting Elements | 2.2.3
496 |  | 21 13 00.00 40 | 2 | Shop Drawings | Fire-Department Connections | 2.2.4
497 |  | 21 13 00.00 40 | 2 | Shop Drawings | Sprinkler Heads | 2.2.6
498 |  | 21 13 00.00 40 | 2 | Shop Drawings | Valves | 2.2.7
499 |  | 21 13 00.00 40 | 3 | Product Data | Underground Piping Materials | 2.2.1
500 |  | 21 13 00.00 40 | 3 | Product Data | Aboveground Piping Materials | 2.2.2
501 |  | 21 13 00.00 40 | 3 | Product Data | Valves | 2.2.7
502 |  | 21 13 00.00 40 | 3 | Product Data | Fire-Department Connections | 2.2.4
503 |  | 21 13 00.00 40 | 3 | Product Data | Riser Alarm Equipment | 2.2.5
504 |  | 21 13 00.00 40 | 3 | Product Data | Sprinkler Heads | 2.2.6
505 |  | 21 13 00.00 40 | 3 | Product Data | Materials | 2.3
506 |  | 21 13 00.00 40 | 3 | Product Data | Supporting Elements | 2.2.3
507 |  | 21 13 00.00 40 | 3 | Product Data | Equipment and Performance Data | 2.1
508 |  | 21 13 00.00 40 | 3 | Product Data | Equipment Labels | 2.2.10
509 |  | 21 13 00.00 40 | 3 | Product Data | Equipment-Label Schedule | 2.2.10
510 |  | 21 13 00.00 40 | 5 | Design Data | Design Analysis and Calculations | Part 2
511 |  | 21 13 00.00 40 | 6 | Test Reports | Pressure Tests | 3.3.6
512 |  | 21 13 00.00 40 | 6 | Test Reports | System Operating Tests | 3.3.3
513 |  | 21 13 00.00 40 | 6 | Test Reports | Air Tests | 3.3.3
514 |  | 21 13 00.00 40 | 6 | Test Reports | Valve-Operating Tests | 3.3.3
515 |  | 21 13 00.00 40 | 6 | Test Reports | Drainage Tests | 3.3.3
516 |  | 21 13 00.00 40 | 10 | Operation and Maintenance Data | Valve Schedules | 2.2.14
517 |  | 21 13 00.00 40 | 10 | Operation and Maintenance Data | Equipment-Label Schedule | 2.2.10
518 |  | 21 13 13 | 1 | Preconstruction Submittals | Qualified Fire Protection Engineer (QFPE) | 1.2.4
519 |  | 21 13 13 | 1 | Preconstruction Submittals | Sprinkler System Designer | 1.4.2.1
520 |  | 21 13 13 | 1 | Preconstruction Submittals | Sprinkler System Installer | 1.4.2.2
521 |  | 21 13 13 | 2 | Shop Drawings | Shop Drawing | 1.2.2.1
522 |  | 21 13 13 | 2 | Shop Drawings | Seismic Bracing | 2.2.15
523 |  | 21 13 13 | 3 | Product Data | Pipe | 2.2
524 |  | 21 13 13 | 3 | Product Data | Fittings | 2.2
525 |  | 21 13 13 | 3 | Product Data | Valves | 2.2.16
526 |  | 21 13 13 | 3 | Product Data | Relief Valves | 2.7.4
527 |  | 21 13 13 | 3 | Product Data | Sprinklers | 2.6
528 |  | 21 13 13 | 3 | Product Data | Pipe Hangers and Supports | 2.2.15
529 |  | 21 13 13 | 3 | Product Data | Sprinkler Alarm Switch | 2.3.2
530 |  | 21 13 13 | 3 | Product Data | Valve Supervisory (Tamper) Switch | 2.3.4
531 |  | 21 13 13 | 3 | Product Data | Fire Department Connection | 2.5
532 |  | 21 13 13 | 3 | Product Data | Backflow Prevention Assembly | 2.4
533 |  | 21 13 13 | 3 | Product Data | Air Vent | 2.7.5
534 |  | 21 13 13 | 3 | Product Data | Hose Valve | 2.4.1
535 |  | 21 13 13 | 3 | Product Data | Nameplates | 2.1.2
536 |  | 21 13 13 | 3 | Product Data | Electrically Operated Alarm Bell | 2.3.1
537 |  | 21 13 13 | 3 | Product Data | Pressure Switches | 2.3.3
538 |  | 21 13 13 | 3 | Product Data | Alarm Initiating And Supervisory Devices | 2.3
539 |  | 21 13 13 | 5 | Design Data | Hydraulic Calculations | 1.2.2.2
540 |  | 21 13 13 | 6 | Test Reports | Test Procedures | 3.7.1
541 |  | 21 13 13 | 7 | Certificates | Verification of Compliant Installation | 3.7.2.1
542 |  | 21 13 13 | 7 | Certificates | Request for Government Final Test | 3.7.2.2
543 |  | 21 13 13 | 10 | Operation and Maintenance Data | Operating and Maintenance (O&M) Instructions | 3.9
544 |  | 21 13 13 | 10 | Operation and Maintenance Data | Spare Parts | 1.6
545 |  | 21 13 13 | 11 | Closeout Submittals | As-built drawings | 3.9
546 |  | 22 00 00 | 2 | Shop Drawings | Plumbing System | 3.9.1
547 |  | 22 00 00 | 2 | Shop Drawings | Plumbing System | 3.12
548 |  | 22 00 00 | 2 | Shop Drawings | Pipe Hangers, Inserts, And Supports | 2.2
549 |  | 22 00 00 | 3 | Product Data | Backflow Prevention Assemblies | 3.9.1.1
550 |  | 22 00 00 | 3 | Product Data | Flush Valve Water Closets | 2.4.2
551 |  | 22 00 00 | 3 | Product Data | Flush Valve Urinals | 2.4.3
552 |  | 22 00 00 | 3 | Product Data | Wall Hung Lavatories | 2.4.4
553 |  | 22 00 00 | 3 | Product Data | Drinking-Water Coolers | 2.4.5
554 |  | 22 00 00 | 3 | Product Data | Water Heaters | 2.8
555 |  | 22 00 00 | 3 | Product Data | Pumps | 2.11
556 |  | 22 00 00 | 3 | Product Data | Welding | 1.6.2
557 |  | 22 00 00 | 3 | Product Data | Vibration-Absorbing Features | 3.4
558 |  | 22 00 00 | 3 | Product Data | Plumbing System | 3.9.1
559 |  | 22 00 00 | 3 | Product Data | Plumbing System | 3.12
560 |  | 22 00 00 | 3 | Product Data | Pipe Sleeves | 2.15.2
561 |  | 22 00 00 | 3 | Product Data | Fixtures | 2.4
562 |  | 22 00 00 | 6 | Test Reports | Tests, Flushing and Disinfection | 3.9
563 |  | 22 00 00 | 6 | Test Reports | Test of Backflow Prevention Assemblies | 3.9.1.1
564 |  | 22 00 00 | 6 | Test Reports | Water Heaters | 2.8
565 |  | 22 00 00 | 7 | Certificates | Materials and Equipment | 1.3
566 |  | 22 00 00 | 7 | Certificates | Bolts | 2.1.1
567 |  | 22 00 00 | 7 | Certificates | Utility Department | 1.4
568 |  | 22 00 00 | 7 | Certificates | Qualification Of Plumbing Contractor | 1.6.1
569 |  | 22 00 00 | 7 | Certificates | Instruction To Government Personnel | 1.9
570 |  | 22 00 00 | 7 | Certificates | Meters And Gages | 2.14
571 |  | 22 00 00 | 10 | Operation and Maintenance Data | Plumbing System | 3.9.1
572 |  | 22 00 00 | 10 | Operation and Maintenance Data | Plumbing System | 3.12
573 |  | 22 00 00 | 10 | Operation and Maintenance Data | Meters And Gages | 2.14
574 |  | 22 00 00 | 11 | Closeout Submittals | Plumbing System | 3.9.1
575 |  | 22 00 00 | 11 | Closeout Submittals | Plumbing System | 3.12
576 |  | 22 05 48.00 20 | 3 | Product Data | Pipe Guides | 2.7
577 |  | 22 05 48.00 20 | 3 | Product Data | Vertical Stops | 3.1.3
578 |  | 22 05 48.00 20 | 3 | Product Data | Machinery Manufacturer's Sound Data | 1.4.2
579 |  | 22 05 48.00 20 | 3 | Product Data | Elastomeric Isolation Pads | 2.2
580 |  | 22 05 48.00 20 | 3 | Product Data | Suspension Isolators | 2.6
581 |  | 22 05 48.00 20 | 5 | Design Data | Machinery | 1.4.3
582 |  | 22 05 48.00 20 | 6 | Test Reports | Equipment Vibration Tests | 3.2.3.1
583 |  | 22 05 48.00 20 | 6 | Test Reports | Protected Spring Isolators | 2.5
584 |  | 22 05 48.00 20 | 8 | Manufacturer's Instructions | Vibration and Noise Isolation Components | 3.1.1
585 |  | 22 13 00 | 2 | Shop Drawings | Hubless, Cast-Iron Soil Pipe And Fittings | 2.1.3
586 |  | 22 13 00 | 3 | Product Data | Floor Drains | 2.3.1
587 |  | 22 13 00 | 3 | Product Data | Floor Sinks | 2.4
588 |  | 22 13 00 | 3 | Product Data | Piping Materials | 2.1.1
589 |  | 22 13 00 | 10 | Operation and Maintenance Data | Sanitary Waste Piping Specialties | 2.2
590 |  | 23 01 30.41 | 1 | Preconstruction Submittals | Coordination Plan | 3.1.1.2
591 |  | 23 01 30.41 | 1 | Preconstruction Submittals | NADCA Firm | 1.4.1
592 |  | 23 01 30.41 | 1 | Preconstruction Submittals | NADCA Team Assistants | 1.4.1
593 |  | 23 01 30.41 | 1 | Preconstruction Submittals | NADCA Air System Cleaning Specialist (ASCS) | 1.4.1
594 |  | 23 01 30.41 | 1 | Preconstruction Submittals | NADCA Supervisor Qualifications | 1.4.1
595 |  | 23 01 30.41 | 1 | Preconstruction Submittals | Records of Experience in the Field of HVAC System Cleaning | 1.4.2
596 |  | 23 01 30.41 | 1 | Preconstruction Submittals | NADCA Work Execution Schedule | 1.5.1
597 |  | 23 01 30.41 | 3 | Product Data | Safety Data Sheets (SDS) | 1.4.3
598 |  | 23 01 30.41 | 6 | Test Reports | Testing Procedures Summary | 3.3.2
599 |  | 23 01 30.41 | 6 | Test Reports | Post-Project Report | 3.3.2
600 |  | 23 05 15 | 1 | Preconstruction Submittals | Material, Equipment, and Fixture Lists | 1.2
601 |  | 23 05 15 | 2 | Shop Drawings | Record Drawings | 1.2
602 |  | 23 05 15 | 2 | Shop Drawings | Connection Diagrams | 1.2
603 |  | 23 05 15 | 2 | Shop Drawings | Coordination Drawings | 1.2
604 |  | 23 05 15 | 2 | Shop Drawings | Fabrication Drawings | 1.2
605 |  | 23 05 15 | 2 | Shop Drawings | Installation Drawings | 3.1
606 |  | 23 05 15 | 3 | Product Data | Pipe and Fittings | 2.1
607 |  | 23 05 15 | 3 | Product Data | Piping Specialties | 2.2
608 |  | 23 05 15 | 3 | Product Data | Valves | 2.3
609 |  | 23 05 15 | 3 | Product Data | Miscellaneous Materials | 2.4
610 |  | 23 05 15 | 3 | Product Data | Supporting Elements | 2.5
611 |  | 23 05 15 | 3 | Product Data | Equipment Foundation Data | 1.2
612 |  | 23 05 15 | 4 | Samples | Manufacturer's Standard Color Charts | 1.2
613 |  | 23 05 15 | 5 | Design Data | Pipe and Fittings | 2.1
614 |  | 23 05 15 | 5 | Design Data | Piping Specialties | 2.2
615 |  | 23 05 15 | 5 | Design Data | Valves | 2.3
616 |  | 23 05 15 | 6 | Test Reports | Hydrostatic Tests | 3.1
617 |  | 23 05 15 | 6 | Test Reports | Air Tests | 3.1
618 |  | 23 05 15 | 6 | Test Reports | Valve-Operating Tests | 3.1
619 |  | 23 05 15 | 6 | Test Reports | Drainage Tests | 3.1
620 |  | 23 05 15 | 6 | Test Reports | Pneumatic Tests | 3.1
621 |  | 23 05 15 | 6 | Test Reports | Non-Destructive Electric Tests | 3.1
622 |  | 23 05 15 | 6 | Test Reports | System Operation Tests | 3.1
623 |  | 23 05 15 | 7 | Certificates | Record of Satisfactory Field Operation | 1.4.2
624 |  | 23 05 15 | 7 | Certificates | List of Qualified Permanent Service Organizations | 1.4.3
625 |  | 23 05 15 | 7 | Certificates | Listing of Product Installations | 1.2
626 |  | 23 05 15 | 7 | Certificates | Records of Existing Conditions | 1.2
627 |  | 23 05 15 | 7 | Certificates | Surface Resistance | 3.1
628 |  | 23 05 15 | 7 | Certificates | Shear and Tensile Strengths | 3.1
629 |  | 23 05 15 | 7 | Certificates | Temperature Ratings | 3.1
630 |  | 23 05 15 | 7 | Certificates | Bending Tests | 3.1
631 |  | 23 05 15 | 7 | Certificates | Flattening Tests | 3.1
632 |  | 23 05 15 | 7 | Certificates | Transverse Guided Weld Bend Tests | 3.1
633 |  | 23 05 15 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.9
634 |  | 23 05 93 | 2 | Shop Drawings | TAB Schematic Drawings and Report Forms | 1.3.3
635 |  | 23 05 93 | 3 | Product Data | Equipment and Performance Data | 1.3
636 |  | 23 05 93 | 3 | Product Data | TAB Related HVAC Submittals | 3.3
637 |  | 23 05 93 | 6 | Test Reports | Certified Final DALT Report | 3.12
638 |  | 23 05 93 | 6 | Test Reports | Certified Tab Reports | 1.5
639 |  | 23 05 93 | 7 | Certificates | Independent TAB Agency and Personnel Qualifications | 1.6.1
640 |  | 23 05 93 | 7 | Certificates | DALT and TAB Submittal and Work Schedule | 3.4
641 |  | 23 07 00 | 2 | Shop Drawings | MICA Plates | 3.2.2.4
642 |  | 23 07 00 | 2 | Shop Drawings | Pipe Insulation Systems | 2.3
643 |  | 23 07 00 | 2 | Shop Drawings | Pipe Insulation Systems | 3.2
644 |  | 23 07 00 | 2 | Shop Drawings | Duct Insulation Systems | 3.3
645 |  | 23 07 00 | 2 | Shop Drawings | Equipment Insulation Systems | 3.4
646 |  | 23 07 00 | 2 | Shop Drawings | Recycled content for insulation materials | 2.3.1
647 |  | 23 07 00 | 3 | Product Data | Pipe Insulation Systems | 2.3
648 |  | 23 07 00 | 3 | Product Data | Pipe Insulation Systems | 3.2
649 |  | 23 07 00 | 3 | Product Data | Duct Insulation Systems | 3.3
650 |  | 23 07 00 | 3 | Product Data | Equipment Insulation Systems | 3.4
651 |  | 23 07 00 | 4 | Samples | Thermal Insulation | 2.2.1.3
652 |  | 23 07 00 | 4 | Samples | Display Samples | 3.1.1
653 |  | 23 07 00 | 7 | Certificates | Indoor air quality for adhesives | 2.2.1
654 |  | 23 07 00 | 8 | Manufacturer's Instructions | Pipe Insulation Systems | 2.3
655 |  | 23 07 00 | 8 | Manufacturer's Instructions | Pipe Insulation Systems | 3.2
656 |  | 23 07 00 | 8 | Manufacturer's Instructions | Duct Insulation Systems | 3.3
657 |  | 23 07 00 | 8 | Manufacturer's Instructions | Equipment Insulation Systems | 3.4
658 |  | 23 09 00 | 2 | Shop Drawings | DDC Contractor Design Drawings | 3.2
659 |  | 23 09 00 | 2 | Shop Drawings | Draft As-Built Drawings | 3.2
660 |  | 23 09 00 | 2 | Shop Drawings | Final As-Built Drawings | 3.2
661 |  | 23 09 00 | 3 | Product Data | Programming Software | 1.8.1
662 |  | 23 09 00 | 3 | Product Data | Programming Software | 1.8.5
663 |  | 23 09 00 | 3 | Product Data | Controller Application Programs | 1.8.2
664 |  | 23 09 00 | 3 | Product Data | Controller Application Programs | 1.8.6
665 |  | 23 09 00 | 3 | Product Data | Configuration Software | 1.8.3
666 |  | 23 09 00 | 3 | Product Data | Controller Configuration Settings | 1.8.4
667 |  | 23 09 00 | 3 | Product Data | Proprietary Multi-Split Engineering Tool Software | 1.1.1.3
668 |  | 23 09 00 | 3 | Product Data | Manufacturer's Product Data | 2.2
669 |  | 23 09 00 | 3 | Product Data | XIF files | 2.2.1
670 |  | 23 09 00 | 3 | Product Data | Draft LNS Database | 3.4.3
671 |  | 23 09 00 | 3 | Product Data | Final LNS Database | 3.5.4
672 |  | 23 09 00 | 3 | Product Data | LNS Plug-ins | 1.8.7
673 |  | 23 09 00 | 3 | Product Data | Niagara Framework Supervisory Gateway Backups | 1.8.9
674 |  | 23 09 00 | 3 | Product Data | Niagara Framework Engineering Tool | 1.8.10
675 |  | 23 09 00 | 3 | Product Data | Niagara Framework Wizards | 1.8.8
676 |  | 23 09 00 | 5 | Design Data | Boiler Or Chiller Plant Gateway Request | 1.9
677 |  | 23 09 00 | 6 | Test Reports | Pre-Construction Quality Control (QC) Checklist | 1.10.1
678 |  | 23 09 00 | 6 | Test Reports | Post-Construction Quality Control (QC) Checklist | 1.10.2
679 |  | 23 09 00 | 6 | Test Reports | Start-Up Testing Report | 3.4.2
680 |  | 23 09 00 | 6 | Test Reports | PVT Procedures | 3.5.1
681 |  | 23 09 00 | 6 | Test Reports | PVT Report | 3.5.3
682 |  | 23 09 00 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | 3.6
683 |  | 23 09 00 | 10 | Operation and Maintenance Data | Training Documentation | 3.8.1
684 |  | 23 09 00 | 11 | Closeout Submittals | Enclosure Keys | 2.5
685 |  | 23 09 00 | 11 | Closeout Submittals | Password Summary Report | 3.1.6.1
686 |  | 23 09 00 | 11 | Closeout Submittals | Closeout Quality Control (QC) Checklist | 1.10.3
687 |  | 23 09 13.34 40 | 2 | Shop Drawings | Fabrication Drawings | 1.2
688 |  | 23 09 13.34 40 | 2 | Shop Drawings | Installation Drawings | 3.1
689 |  | 23 09 13.34 40 | 3 | Product Data | Rate-of-Flow Controller | 2.1
690 |  | 23 09 13.34 40 | 3 | Product Data | Nonmodulating Float Valve | 2.2
691 |  | 23 09 13.34 40 | 3 | Product Data | Water Pressure Regulating Valve | 2.3
692 |  | 23 09 13.34 40 | 3 | Product Data | Water Pressure Relief Valve | 2.4
693 |  | 23 09 13.34 40 | 3 | Product Data | Pilot-Operated Pressure Relief Valve | 2.5
694 |  | 23 09 13.34 40 | 3 | Product Data | Sample Warranty | 1.4
695 |  | 23 09 13.34 40 | 7 | Certificates | List of Product Installations | 1.2
696 |  | 23 09 13.34 40 | 7 | Certificates | Certificates of Conformance | 1.4
697 |  | 23 09 13.34 40 | 7 | Certificates | Manufacturer's Warranty | 3.3
698 |  | 23 09 13.34 40 | 6 | Test Reports | Test Reports | 3.2.1
699 |  | 23 09 53.00 20 | 2 | Shop Drawings | Control System Diagrams | 1.7.1
700 |  | 23 09 53.00 20 | 2 | Shop Drawings | Ladder Diagram | 1.7.2
701 |  | 23 09 53.00 20 | 2 | Shop Drawings | Operating Parameters | 1.7.3
702 |  | 23 09 53.00 20 | 2 | Shop Drawings | Automatic Control Valve Schedules | 1.7.4
703 |  | 23 09 53.00 20 | 2 | Shop Drawings | Damper Schedules | 1.7.5
704 |  | 23 09 53.00 20 | 2 | Shop Drawings | Sequence of Operation | 1.7.8
705 |  | 23 09 53.00 20 | 2 | Shop Drawings | Arrangement Drawing | 1.7.9
706 |  | 23 09 53.00 20 | 2 | Shop Drawings | Wiring Diagram | 1.7.6
707 |  | 23 09 53.00 20 | 2 | Shop Drawings | Compressed Air Station Schematic | 1.7.7
708 |  | 23 09 53.00 20 | 2 | Shop Drawings | Control Panel Schematics | 1.7.7
709 |  | 23 09 53.00 20 | 3 | Product Data | Actuators | 2.2
710 |  | 23 09 53.00 20 | 3 | Product Data | Valves | 2.3
711 |  | 23 09 53.00 20 | 3 | Product Data | Dampers | 2.4
712 |  | 23 09 53.00 20 | 3 | Product Data | Fire Protection Devices | 2.5
713 |  | 23 09 53.00 20 | 3 | Product Data | Sensors | 2.6
714 |  | 23 09 53.00 20 | 3 | Product Data | Thermostats | 2.8
715 |  | 23 09 53.00 20 | 3 | Product Data | Sunshields | 2.9
716 |  | 23 09 53.00 20 | 3 | Product Data | Pressure Switches | 2.10.1
717 |  | 23 09 53.00 20 | 3 | Product Data | Indicating Devices | 2.11
718 |  | 23 09 53.00 20 | 3 | Product Data | Controllers | 2.13
719 |  | 23 09 53.00 20 | 3 | Product Data | Pressure Gages | 2.12
720 |  | 23 09 53.00 20 | 3 | Product Data | Control Panels | 2.15
721 |  | 23 09 53.00 20 | 6 | Test Reports | Commissioning Procedures | 1.9.6
722 |  | 23 09 53.00 20 | 6 | Test Reports | Calibration Adjustment And Commissioning Reports | 1.9.7
723 |  | 23 09 53.00 20 | 6 | Test Reports | Site Testing Procedures | 1.9.5
724 |  | 23 09 53.00 20 | 6 | Test Reports | Performance Verification Test | 3.3.5
725 |  | 23 09 53.00 20 | 7 | Certificates | Certification of Completion | 3.3.4
726 |  | 23 09 53.00 20 | 8 | Manufacturer's Instructions | Training Course Documentation | 3.4.1
727 |  | 23 09 53.00 20 | 10 | Operation and Maintenance Data | Space Temperature Control System | 1.9.8
728 |  | 23 09 53.00 20 | 11 | Closeout Submittals | Qualified Service Organization List | 3.5
729 |  | 23 11 20 | 2 | Shop Drawings | Gas Piping System | 1.5.4
730 |  | 23 11 20 | 2 | Shop Drawings | Gas Piping System | 2.2
731 |  | 23 11 20 | 2 | Shop Drawings | Gas Piping System | 3.3
732 |  | 23 11 20 | 2 | Shop Drawings | Coordination Drawings | 1.5.4
733 |  | 23 11 20 | 3 | Product Data | Gas Equipment Connectors | 1.5.4
734 |  | 23 11 20 | 3 | Product Data | Gas Piping System | 1.5.4
735 |  | 23 11 20 | 3 | Product Data | Gas Piping System | 2.2
736 |  | 23 11 20 | 3 | Product Data | Gas Piping System | 3.3
737 |  | 23 11 20 | 3 | Product Data | Pipe Coating Materials | 2.1
738 |  | 23 11 20 | 3 | Product Data | Pressure Regulators | 2.6
739 |  | 23 11 20 | 3 | Product Data | Risers | 2.4
740 |  | 23 11 20 | 3 | Product Data | Valves | 2.3
741 |  | 23 11 20 | 3 | Product Data | Warning and Identification Tape | 2.2.4
742 |  | 23 11 20 | 6 | Test Reports | Testing | 3.17
743 |  | 23 11 20 | 6 | Test Reports | Pressure Tests | 3.17.1
744 |  | 23 11 20 | 6 | Test Reports | Test with Gas | 3.17.2
745 |  | 23 11 20 | 7 | Certificates | Welders Procedures and Qualifications | 1.5.2
746 |  | 23 11 20 | 7 | Certificates | Assigned Number, Letter, or Symbol | 1.5.2
747 |  | 23 11 20 | 7 | Certificates | Designer Qualifications | 1.5.1
748 |  | 23 11 20 | 8 | Manufacturer's Instructions | Pipe Coating Materials | 2.1
749 |  | 23 11 20 | 10 | Operation and Maintenance Data | Gas Facility System and Equipment Operation | 1.3.1
750 |  | 23 11 20 | 10 | Operation and Maintenance Data | Gas Facility System Maintenance | 1.3.2
751 |  | 23 11 20 | 10 | Operation and Maintenance Data | Gas Facility Equipment Maintenance | 1.3.3
752 |  | 23 21 13.00 20 | 2 | Shop Drawings | Hot water heating system | 1.3.1
753 |  | 23 21 13.00 20 | 3 | Product Data | Pumps | 2.3.1
754 |  | 23 21 13.00 20 | 3 | Product Data | Expansion tanks | 2.3.2
755 |  | 23 21 13.00 20 | 3 | Product Data | Backflow preventers | 2.3.4
756 |  | 23 21 13.00 20 | 3 | Product Data | External air separation tanks | 2.3.3
757 |  | 23 21 13.00 20 | 3 | Product Data | Hot water heating pipe | 2.1.1
758 |  | 23 21 13.00 20 | 6 | Test Reports | Hydrostatic test of piping system | 3.3.1
759 |  | 23 21 13.00 20 | 6 | Test Reports | Auxiliary equipment and accessory tests | 3.3.2
760 |  | 23 21 13.00 20 | 7 | Certificates | Backflow preventer certification | 1.5.4
761 |  | 23 21 13.00 20 | 7 | Certificates | Report of prior installations | 1.5.2.1
762 |  | 23 21 13.00 20 | 7 | Certificates | Welding procedures | 1.5.2.2
763 |  | 23 21 13.00 20 | 7 | Certificates | Welder's qualifications | 1.5.2.3
764 |  | 23 21 23 | 2 | Shop Drawings | System Coordination | 2.1.2
765 |  | 23 21 23 | 3 | Product Data | Instructions | 2.2.2
766 |  | 23 21 23 | 3 | Product Data | Equipment Data | 2.2.5
767 |  | 23 21 23 | 3 | Product Data | Training Period | 3.5.2
768 |  | 23 21 23 | 6 | Test Reports | Factory Tests | 2.6
769 |  | 23 21 23 | 6 | Test Reports | Field Quality Control | 3.3
770 |  | 23 21 23 | 7 | Certificates | Manufacturer's Representative | 1.3.1
771 |  | 23 21 23 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.5.1
772 |  | 23 21 23 | 10 | Operation and Maintenance Data | Training | 3.5.2
773 |  | 23 30 00 | 2 | Shop Drawings | Detail Drawings | 1.4.4
774 |  | 23 30 00 | 3 | Product Data | Metallic Flexible Duct | 2.9.1.1
775 |  | 23 30 00 | 3 | Product Data | Insulated Nonmetallic Flexible Duct Runouts | 2.9.1.2
776 |  | 23 30 00 | 3 | Product Data | Duct Connectors | 2.9.1.2
777 |  | 23 30 00 | 3 | Product Data | Duct Access Doors | 2.9.2
778 |  | 23 30 00 | 3 | Product Data | Fire Dampers | 2.9.3
779 |  | 23 30 00 | 3 | Product Data | Manual Balancing Dampers | 2.9.4
780 |  | 23 30 00 | 3 | Product Data | Sound Attenuation Equipment | 2.9.8
781 |  | 23 30 00 | 3 | Product Data | Acoustical Duct Liner | 2.9.8.3
782 |  | 23 30 00 | 3 | Product Data | Diffusers | 2.9.9.1
783 |  | 23 30 00 | 3 | Product Data | Registers and Grilles | 2.9.9.3
784 |  | 23 30 00 | 3 | Product Data | Louvers | 2.9.10
785 |  | 23 30 00 | 3 | Product Data | Air Vents, Penthouses, and Goosenecks | 2.9.11
786 |  | 23 30 00 | 3 | Product Data | Centrifugal Fans | 2.10.1.1
787 |  | 23 30 00 | 3 | Product Data | Centrifugal Type Power Roof Ventilators | 2.10.1.2
788 |  | 23 30 00 | 3 | Product Data | Air-Curtain Fans | 2.10.1.3
789 |  | 23 30 00 | 3 | Product Data | Air Handling Units | 2.11
790 |  | 23 30 00 | 3 | Product Data | Constant Volume, Single Duct Terminal Units | 2.12.1.1
791 |  | 23 30 00 | 3 | Product Data | Variable Volume, Single Duct Terminal Units | 2.12.1.2
792 |  | 23 30 00 | 3 | Product Data | Reheat Units | 2.12.1.3
793 |  | 23 30 00 | 3 | Product Data | Test Procedures | 1.4.5
794 |  | 23 30 00 | 3 | Product Data | Indoor Air Quality for Duct Sealants | 2.9.1
795 |  | 23 30 00 | 6 | Test Reports | Performance Tests | 3.12
796 |  | 23 30 00 | 6 | Test Reports | Damper Acceptance Test | 3.1
797 |  | 23 30 00 | 7 | Certificates | Ozone Depleting Substances Technician Certification | 1.4.3
798 |  | 23 30 00 | 8 | Manufacturer's Instructions | Manufacturer's Installation Instructions | 3.2
799 |  | 23 30 00 | 8 | Manufacturer's Instructions | Operation and Maintenance Training | 3.14.2
800 |  | 23 30 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.14.1
801 |  | 23 30 00 | 10 | Operation and Maintenance Data | Fire Dampers | 2.9.3
802 |  | 23 30 00 | 10 | Operation and Maintenance Data | Manual Balancing Dampers | 2.9.4
803 |  | 23 30 00 | 10 | Operation and Maintenance Data | Centrifugal Fans | 2.10.1.1
804 |  | 23 30 00 | 10 | Operation and Maintenance Data | Centrifugal Type Power Roof Ventilators | 2.10.1.2
805 |  | 23 30 00 | 10 | Operation and Maintenance Data | Air-Curtain Fans | 2.10.1.3
806 |  | 23 30 00 | 10 | Operation and Maintenance Data | Air Handling Units | 2.11
807 |  | 23 30 00 | 10 | Operation and Maintenance Data | Constant Volume, Single Duct Terminal Units | 2.12.1.1
808 |  | 23 30 00 | 10 | Operation and Maintenance Data | Variable Volume, Single Duct Terminal Units | 2.12.1.2
809 |  | 23 30 00 | 10 | Operation and Maintenance Data | Reheat Units | 2.12.1.3
810 |  | 23 30 00 | 11 | Closeout Submittals | Indoor Air Quality During Construction | 3.13
811 |  | 23 31 13.00 40 | 1 | Preconstruction Submittals | Material, Equipment, and Fixture Lists | Part 2
812 |  | 23 31 13.00 40 | 1 | Preconstruction Submittals | Records of Existing Conditions | 2.1.1
813 |  | 23 31 13.00 40 | 2 | Shop Drawings | Connection Diagrams | 2.1
814 |  | 23 31 13.00 40 | 2 | Shop Drawings | Offset Fitting Configurations | 2.2.1
815 |  | 23 31 13.00 40 | 3 | Product Data | Equipment and Performance Data | 2.1.1
816 |  | 23 31 13.00 40 | 3 | Product Data | Galvanized Steel Ductwork Materials | 2.3.1
817 |  | 23 31 13.00 40 | 3 | Product Data | Brazing Materials | 2.3.2
818 |  | 23 31 13.00 40 | 3 | Product Data | Mill-Rolled Reinforcing and Supporting Materials | 2.3.3
819 |  | 23 31 13.00 40 | 3 | Product Data | Round Sheet Metal Duct Fittings | 2.2.1
820 |  | 23 31 13.00 40 | 3 | Product Data | Round, High-Pressure, Double-Wall Sheet Metal Ducts | 2.2.2
821 |  | 23 31 13.00 40 | 3 | Product Data | Turning Vanes | 2.2.5
822 |  | 23 31 13.00 40 | 3 | Product Data | Flexible Connectors | 2.2.7
823 |  | 23 31 13.00 40 | 3 | Product Data | Flexible Duct Materials | 2.2.10
824 |  | 23 31 13.00 40 | 3 | Product Data | Power-Operated Dampers | 2.2.13
825 |  | 23 31 13.00 40 | 3 | Product Data | Fire Dampers and Wall Collars | 2.2.14
826 |  | 23 31 13.00 40 | 3 | Product Data | Gravity Backdraft and Relief Dampers | 2.2.12
827 |  | 23 31 13.00 40 | 3 | Product Data | Manual Volume Dampers | 2.2.11
828 |  | 23 31 13.00 40 | 5 | Design Data | Design Analysis and Calculations | 2.1.1
829 |  | 23 31 13.00 40 | 6 | Test Reports | Ductwork Leakage Tests | 3.4.1
830 |  | 23 31 13.00 40 | 7 | Certificates | Listing of Product Installations | 1.3
831 |  | 23 31 13.00 40 | 7 | Certificates | Galvanized Steel Ductwork Materials | 2.3.1
832 |  | 23 31 13.00 40 | 7 | Certificates | Brazing Materials | 2.3.2
833 |  | 23 31 13.00 40 | 7 | Certificates | Mill-Rolled Reinforcing and Supporting Materials | 2.3.3
834 |  | 23 31 13.00 40 | 7 | Certificates | Round Sheet Metal Duct Fittings | 2.2.1
835 |  | 23 31 13.00 40 | 7 | Certificates | Round, High-Pressure, Double-Wall Sheet Metal Ducts | 2.2.2
836 |  | 23 31 13.00 40 | 7 | Certificates | Turning Vanes | 2.2.5
837 |  | 23 31 13.00 40 | 7 | Certificates | Dampers | 2.2.6
838 |  | 23 31 13.00 40 | 7 | Certificates | Flexible Connectors | 2.2.7
839 |  | 23 31 13.00 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.5.1
840 |  | 23 31 13.00 40 | 10 | Operation and Maintenance Data | Power Operated Dampers | 2.2.13
841 |  | 23 31 13.00 40 | 10 | Operation and Maintenance Data | Fire Dampers and Wall Collars | 2.2.14
842 |  | 23 31 13.00 40 | 11 | Closeout Submittals | Record Drawings | 3.5.2
843 |  | 23 34 23.00 40 | 2 | Shop Drawings | Shop Drawings | 2.1.1
844 |  | 23 34 23.00 40 | 2 | Shop Drawings | Installation Drawings | 3.1
845 |  | 23 34 23.00 40 | 3 | Product Data | Housing | 2.2.1
846 |  | 23 34 23.00 40 | 3 | Product Data | Fan | 2.2.2
847 |  | 23 34 23.00 40 | 3 | Product Data | Motor | 2.2.3
848 |  | 23 34 23.00 40 | 3 | Product Data | Bases | 2.2.4
849 |  | 23 34 23.00 40 | 3 | Product Data | Roof Curbs | 2.2.5
850 |  | 23 34 23.00 40 | 3 | Product Data | Dampers | 2.2.6
851 |  | 23 34 23.00 40 | 3 | Product Data | Screens | 2.2.7
852 |  | 23 34 23.00 40 | 3 | Product Data | Sound Baffles | 2.2.8
853 |  | 23 34 23.00 40 | 11 | Closeout Submittals | Record Drawings | 3.3
854 |  | 23 36 00.00 40 | 1 | Preconstruction Submittals | Records of Existing Conditions | 1.2.1
855 |  | 23 36 00.00 40 | 2 | Shop Drawings | Bypass Single-Duct Air Terminal Units | 2.1.2
856 |  | 23 36 00.00 40 | 3 | Product Data | Bypass Single-Duct Air Terminal Units | 2.1.2
857 |  | 23 36 00.00 40 | 6 | Test Reports | Test Report | 3.2
858 |  | 23 36 00.00 40 | 7 | Certificates | List of Spare Parts | 1.2.1
859 |  | 23 36 00.00 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.4.1
860 |  | 23 36 00.00 40 | 11 | Closeout Submittals | Record Drawings | 3.4.1
861 |  | 23 37 13.00 40 | 1 | Preconstruction Submittals | Material, Equipment, and Fixture Lists | 2.2.1
862 |  | 23 37 13.00 40 | 1 | Preconstruction Submittals | Records of Existing Conditions | 2.2.1
863 |  | 23 37 13.00 40 | 2 | Shop Drawings | Fabrication Drawings | 2.2.1
864 |  | 23 37 13.00 40 | 2 | Shop Drawings | Installation Drawings | 3.1
865 |  | 23 37 13.00 40 | 3 | Product Data | Equipment and Performance Data | 2.1
866 |  | 23 37 13.00 40 | 4 | Samples | Manufacturer's Standard Color Chart | 2.2.1
867 |  | 23 52 00 | 2 | Shop Drawings | Detail Drawings | 1.5
868 |  | 23 52 00 | 3 | Product Data | Materials and Equipment | 2.1.1
869 |  | 23 52 00 | 3 | Product Data | Spare Parts | 1.5
870 |  | 23 52 00 | 3 | Product Data | Water Treatment System | 2.13
871 |  | 23 52 00 | 3 | Product Data | Boiler Water Treatment | 2.13
872 |  | 23 52 00 | 3 | Product Data | Heating System Tests | 3.9
873 |  | 23 52 00 | 3 | Product Data | Fuel System Tests | 3.12
874 |  | 23 52 00 | 3 | Product Data | Unit Heaters | 2.6
875 |  | 23 52 00 | 3 | Product Data | Welding | 1.3
876 |  | 23 52 00 | 3 | Product Data | Qualifications | 3.9
877 |  | 23 52 00 | 3 | Product Data | Field Instructions | 3.11
878 |  | 23 52 00 | 3 | Product Data | Tests | 3.4
879 |  | 23 52 00 | 6 | Test Reports | Heating System Tests | 3.9
880 |  | 23 52 00 | 6 | Test Reports | Fuel System Tests | 3.12
881 |  | 23 52 00 | 6 | Test Reports | Water Treatment Testing | 3.9.1
882 |  | 23 52 00 | 7 | Certificates | Bolts | 2.9.6.3
883 |  | 23 52 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Instructions | 3.11
884 |  | 23 52 00 | 10 | Operation and Maintenance Data | Water Treatment System | 2.13
885 |  | 23 52 00 | 11 | Closeout Submittals | Indoor Air Quality During Construction | 3.10.2
886 |  | 23 64 26 | 3 | Product Data | Pumps | 2.3
887 |  | 23 64 26 | 3 | Product Data | Expansion Tanks | 2.4
888 |  | 23 64 26 | 3 | Product Data | Air Separator Tanks | 2.5
889 |  | 23 64 26 | 3 | Product Data | Water Treatment Systems | 2.6
890 |  | 23 64 26 | 6 | Test Reports | Piping Welds NDE Report | 3.1.1.3
891 |  | 23 64 26 | 6 | Test Reports | Pressure Tests Reports | 3.4.2
892 |  | 23 64 26 | 7 | Certificates | Employer's Record Documents (For Welding) | 3.1.1.1
893 |  | 23 64 26 | 7 | Certificates | Welding Procedures and Qualifications | 3.1.1.2
894 |  | 23 64 26 | 8 | Manufacturer's Instructions | Lesson plan for the Instruction Course | 3.5
895 |  | 23 64 26 | 10 | Operation and Maintenance Data | Water Treatment Systems | 2.6
896 |  | 23 64 26 | 10 | Operation and Maintenance Data | Pumps | 2.3
897 |  | 23 64 26 | 10 | Operation and Maintenance Data | Expansion Tanks | 2.4
898 |  | 23 64 26 | 10 | Operation and Maintenance Data | Air Separator Tanks | 2.5
899 |  | 23 73 13.00 40 | 2 | Shop Drawings | Installation Drawings | 3.2
900 |  | 23 73 13.00 40 | 2 | Shop Drawings | Fabrication and Connection Drawings | 2.1
901 |  | 23 73 13.00 40 | 3 | Product Data | Equipment and Performance Data | 2.1
902 |  | 23 73 13.00 40 | 3 | Product Data | Sample Warranty | 1.3.2
903 |  | 23 73 13.00 40 | 3 | Product Data | Air Filter Gauges | 2.2.9.4
904 |  | 23 73 13.00 40 | 3 | Product Data | Coating Specimen | 2.2.2.2
905 |  | 23 73 13.00 40 | 3 | Product Data | Final Test Reports | 3.3.3
906 |  | 23 73 13.00 40 | 7 | Certificates | List of Product Installations | 1.3
907 |  | 23 73 13.00 40 | 7 | Certificates | Certificates of Conformance | 1.3.1
908 |  | 23 73 13.00 40 | 7 | Certificates | Unit Cabinet | 2.2.2
909 |  | 23 73 13.00 40 | 7 | Certificates | Fan | 2.2.3
910 |  | 23 73 13.00 40 | 7 | Certificates | Drain Pans | 2.2.4
911 |  | 23 73 13.00 40 | 7 | Certificates | Insulation | 2.2.5
912 |  | 23 73 13.00 40 | 7 | Certificates | Plenums | 2.2.6
913 |  | 23 73 13.00 40 | 7 | Certificates | Spare Parts | 2.1
914 |  | 23 73 13.00 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.4.1
915 |  | 23 73 13.00 40 | 11 | Closeout Submittals | Warranty | 1.5
916 |  | 23 81 00 | 3 | Product Data | Spare Parts | 3.5.1
917 |  | 23 81 00 | 3 | Product Data | Posted Instructions | 3.4
918 |  | 23 81 00 | 3 | Product Data | Coil Corrosion Protection | 2.5.1
919 |  | 23 81 00 | 3 | Product Data | Training | 3.4
920 |  | 23 81 00 | 3 | Product Data | Inventory | 1.5
921 |  | 23 81 00 | 3 | Product Data | Supplied Products | 2.1
922 |  | 23 81 00 | 3 | Product Data | Manufacturer's Standard Catalog Data | 2.2
923 |  | 23 81 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.4
924 |  | 23 81 00 | 11 | Closeout Submittals | Ozone Depleting Substances | 2.2.2.3
925 |  | 23 82 16.00 40 | 1 | Preconstruction Submittals | Record of Existing Conditions | 1.3
926 |  | 23 82 16.00 40 | 2 | Shop Drawings | Fabrication Drawings | 2.1
927 |  | 23 82 16.00 40 | 2 | Shop Drawings | Connection Diagrams | 2.1
928 |  | 23 82 16.00 40 | 2 | Shop Drawings | Controls Layout | 1.3
929 |  | 23 82 16.00 40 | 2 | Shop Drawings | Internal Tubing and Wiring | 1.3
930 |  | 23 82 16.00 40 | 2 | Shop Drawings | Installation Drawings | 3.1
931 |  | 23 82 16.00 40 | 3 | Product Data | Hot-Water Heating | 2.1
932 |  | 23 82 16.00 40 | 3 | Product Data | Chilled-Water Cooling | 2.1
933 |  | 23 82 16.00 40 | 5 | Design Data | Design Analysis and Calculations | 1.3
934 |  | 23 82 16.00 40 | 6 | Test Reports | Final Test Reports | 3.2
935 |  | 23 82 16.00 40 | 7 | Certificates | Certificates of Conformance | 1.3
936 |  | 23 82 16.00 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | 3.3.1
937 |  | 23 82 16.00 40 | 11 | Closeout Submittals | Record Drawings | 3.3.2
938 |  | 23 82 46.00 40 | 2 | Shop Drawings | Fabrication Drawings | 1.2.1
939 |  | 23 82 46.00 40 | 3 | Product Data | Performance Data | 2.1
940 |  | 23 82 46.00 40 | 3 | Product Data | Electric Unit Heaters | 2.1
941 |  | 23 82 46.00 40 | 3 | Product Data | Heating Element | 2.2.1
942 |  | 23 82 46.00 40 | 3 | Product Data | Controls | 2.2.2
943 |  | 23 82 46.00 40 | 3 | Product Data | Casings | 3.1.1
944 |  | 23 82 46.00 40 | 3 | Product Data | Propellers and Motors | 2.2.3
945 |  | 23 82 46.00 40 | 8 | Manufacturer's Instructions | Manufacturer's Instructions | 1.2.1
946 |  | 26 05 00.00 40 | 2 | Shop Drawings | Marking Strips | 3.2.9.1
947 |  | 26 05 00.00 40 | 3 | Product Data | Conduits and Raceways | 2.1.1
948 |  | 26 05 00.00 40 | 3 | Product Data | Wire and Cable | 2.2.1
949 |  | 26 05 00.00 40 | 3 | Product Data | Splices and Connectors | 3.2.8
950 |  | 26 05 00.00 40 | 3 | Product Data | Switches | 2.2.3
951 |  | 26 05 00.00 40 | 3 | Product Data | Receptacles | 2.2.5
952 |  | 26 05 00.00 40 | 3 | Product Data | Outlet Boxes, Pull Boxes and Junction Boxes | 2.1.3
953 |  | 26 05 00.00 40 | 3 | Product Data | Circuit Breakers | 2.1.4.1
954 |  | 26 05 00.00 40 | 3 | Product Data | Panelboards | 2.1.4
955 |  | 26 05 00.00 40 | 3 | Product Data | Device Plates | 2.2.2
956 |  | 26 05 00.00 40 | 6 | Test Reports | Continuity Test | 3.6
957 |  | 26 05 00.00 40 | 6 | Test Reports | Phase-Rotation Tests | 3.6
958 |  | 26 05 00.00 40 | 6 | Test Reports | Insulation Resistance Test | 3.6
959 |  | 26 05 00.00 40 | 6 | Test Reports | 600-Volt Wiring Test | 3.6
960 |  | 26 05 00.00 40 | 6 | Test Reports | Insulation-Resistance Test | 3.6
961 |  | 26 05 00.00 40 | 8 | Manufacturer's Instructions | Manufacturer's Instructions | 3.1
962 |  | 26 05 26.00 40 | 3 | Product Data | Ground Rods | 2.1.1
963 |  | 26 05 26.00 40 | 3 | Product Data | Ground Wires | 2.1.2
964 |  | 26 05 26.00 40 | 3 | Product Data | Connectors and Fasteners | 2.1.3
965 |  | 26 05 26.00 40 | 3 | Product Data | Conductive Corrosion Inhibiting Compounds | 2.1.4
966 |  | 26 05 26.00 40 | 3 | Product Data | Ground Buses | 2.1.5
967 |  | 26 05 26.00 40 | 6 | Test Reports | Ground Resistance Tests | 3.2.1
968 |  | 26 05 26.00 40 | 6 | Test Reports | Equipment Continuity Test | 3.2.2
969 |  | 26 05 26.00 40 | 7 | Certificates | Ground Resistance Test Equipment | 1.3.3
970 |  | 26 05 26.00 40 | 11 | Closeout Submittals | Record Drawings | 3.3
971 |  | 26 20 00 | 2 | Shop Drawings | Panelboards | 2.1
972 |  | 26 20 00 | 2 | Shop Drawings | Wireways | 2.17
973 |  | 26 20 00 | 2 | Shop Drawings | Marking Strips | 3.1.7.1
974 |  | 26 20 00 | 3 | Product Data | Receptacles | 2.9
975 |  | 26 20 00 | 3 | Product Data | Circuit Breakers | 2.10.3
976 |  | 26 20 00 | 3 | Product Data | Switches | 2.7
977 |  | 26 20 00 | 3 | Product Data | Enclosed Circuit Breakers | 2.11
978 |  | 26 20 00 | 3 | Product Data | Surge Protective Devices | 2.18
979 |  | 26 20 00 | 6 | Test Reports | 600-volt Wiring Test | 3.4.2
980 |  | 26 20 00 | 6 | Test Reports | Grounding System Test | 3.4.3
981 |  | 26 20 00 | 7 | Certificates | Fuses | 2.8
982 |  | 26 20 00 | 7 | Certificates | Electrical Systems | 1.5.1
983 |  | 26 23 00.00 40 | 2 | Shop Drawings | Switchboard Drawings | 2.1.1
984 |  | 26 23 00.00 40 | 3 | Product Data | Switchboard | 2.2
985 |  | 26 23 00.00 40 | 6 | Test Reports | Acceptance Checks and Tests | 3.2.1
986 |  | 26 23 00.00 40 | 7 | Certificates | Equipment Test Schedule | 2.3.1
987 |  | 26 23 00.00 40 | 7 | Certificates | Switchboard Design Tests | 2.3.2
988 |  | 26 23 00.00 40 | 10 | Operation and Maintenance Data | Switchboard Operation and Maintenance | 3.3.1
989 |  | 26 23 00.00 40 | 11 | Closeout Submittals | Warranty | 1.6
990 |  | 26 23 00.00 40 | 11 | Closeout Submittals | Assembled Operation and Maintenance Manuals | 3.3.2
991 |  | 26 23 00.00 40 | 11 | Closeout Submittals | Request for Settings | 3.2
992 |  | 26 28 01.00 10 | 3 | Product Data | Fault Current Analysis | 2.1
993 |  | 26 28 01.00 10 | 3 | Product Data | Protective Device Coordination Study | 2.1
994 |  | 26 28 01.00 10 | 3 | Product Data | System Coordinator | 1.4.1
995 |  | 26 28 21.00 40 | 2 | Shop Drawings | Connection Diagrams | 2.1
996 |  | 26 28 21.00 40 | 2 | Shop Drawings | Fabrication Drawings | 2.1
997 |  | 26 28 21.00 40 | 2 | Shop Drawings | Installation Drawings | 2.1
998 |  | 26 28 21.00 40 | 3 | Product Data | Equipment and Performance Data | 2.1
999 |  | 26 28 21.00 40 | 3 | Product Data | Contacts | 2.2.1
1000 |  | 26 28 21.00 40 | 3 | Product Data | Indicating Lights | 2.2.2
1001 |  | 26 28 21.00 40 | 3 | Product Data | Terminal Board | 2.2.3
1002 |  | 26 28 21.00 40 | 3 | Product Data | Enclosures | 2.2.5
1003 |  | 26 28 21.00 40 | 6 | Test Reports | Qualification Testing | 2.3.1
1004 |  | 26 28 21.00 40 | 6 | Test Reports | Operation Tests | 2.3.1
1005 |  | 26 28 21.00 40 | 7 | Certificates | Listing of Product Installations | 1.3.1
1006 |  | 26 28 21.00 40 | 8 | Manufacturer's Instructions | Manufacturer's Instructions | 3.1
1007 |  | 26 32 15.00 | 2 | Shop Drawings | Engine-Generator Set and Auxiliary Equipment | 2.1.1
1008 |  | 26 32 15.00 | 2 | Shop Drawings | Auxiliary Systems | 1.4.8
1009 |  | 26 32 15.00 | 2 | Shop Drawings | Detailed Drawings | 1.4.7
1010 |  | 26 32 15.00 | 2 | Shop Drawings | Acceptance | 3.17
1011 |  | 26 32 15.00 | 3 | Product Data | Harmonic Requirements | 2.1.8
1012 |  | 26 32 15.00 | 3 | Product Data | Engine-Generator Set Efficiencies | 2.1.1
1013 |  | 26 32 15.00 | 3 | Product Data | Emissions | 2.13
1014 |  | 26 32 15.00 | 3 | Product Data | Filters | 2.7.2
1015 |  | 26 32 15.00 | 3 | Product Data | Special Tools | 2.15
1016 |  | 26 32 15.00 | 3 | Product Data | Remote Alarm Annunciator | 2.14.4
1017 |  | 26 32 15.00 | 3 | Product Data | Engine-Generator Parameter Schedule | 2.1.1
1018 |  | 26 32 15.00 | 3 | Product Data | Generator | 2.16
1019 |  | 26 32 15.00 | 3 | Product Data | Manufacturer's Catalog | 2.5
1020 |  | 26 32 15.00 | 3 | Product Data | Spare Parts | 1.7.2
1021 |  | 26 32 15.00 | 3 | Product Data | Onsite Training | 3.12
1022 |  | 26 32 15.00 | 3 | Product Data | Vibration-Isolation | 2.1.7
1023 |  | 26 32 15.00 | 3 | Product Data | Posted Data and Instructions | 3.16
1024 |  | 26 32 15.00 | 3 | Product Data | Experience | 1.4.5
1025 |  | 26 32 15.00 | 3 | Product Data | Field Engineer | 1.4.6
1026 |  | 26 32 15.00 | 3 | Product Data | General Installation | 3.2
1027 |  | 26 32 15.00 | 3 | Product Data | Exciter | 2.17
1028 |  | 26 32 15.00 | 5 | Design Data | Performance Criteria | 2.16
1029 |  | 26 32 15.00 | 5 | Design Data | Sound Limitations | 2.9
1030 |  | 26 32 15.00 | 5 | Design Data | Integral Main Fuel Storage Tank | 2.6.4
1031 |  | 26 32 15.00 | 5 | Design Data | Power Factor | 3.6.1.2
1032 |  | 26 32 15.00 | 5 | Design Data | Heat Exchanger | 2.8.2
1033 |  | 26 32 15.00 | 5 | Design Data | Time-Delay on Alarms | 2.20.5
1034 |  | 26 32 15.00 | 5 | Design Data | Cooling System | 2.8
1035 |  | 26 32 15.00 | 5 | Design Data | Vibration Isolation | 2.1.7
1036 |  | 26 32 15.00 | 5 | Design Data | Battery Charger | 2.14.3.2
1037 |  | 26 32 15.00 | 5 | Design Data | Capacity Calculations for Engine-Generator Set | 2.1.1
1038 |  | 26 32 15.00 | 5 | Design Data | Brake Mean Effective Pressure (BMEP) Calculations | 2.1.1
1039 |  | 26 32 15.00 | 5 | Design Data | Torsional Vibration Stress Analysis Computations | 2.1.1
1040 |  | 26 32 15.00 | 5 | Design Data | Capacity Calculations for Batteries | 2.1.1
1041 |  | 26 32 15.00 | 5 | Design Data | Turbocharger Load Calculations | 2.1.1
1042 |  | 26 32 15.00 | 6 | Test Reports | Performance Tests | 3.6.9
1043 |  | 26 32 15.00 | 6 | Test Reports | Factory Inspection and Tests | 2.29
1044 |  | 26 32 15.00 | 6 | Test Reports | Factory Tests | 2.29.2
1045 |  | 26 32 15.00 | 6 | Test Reports | Onsite Inspection and Tests | 3.6
1046 |  | 26 32 15.00 | 6 | Test Reports | Acceptance Checks and Tests | 3.9.2
1047 |  | 26 32 15.00 | 6 | Test Reports | Functional Acceptance Tests | 3.10.2
1048 |  | 26 32 15.00 | 6 | Test Reports | Maintenance Procedures | 3.12
1049 |  | 26 32 15.00 | 6 | Test Reports | Operation and Maintenance Manuals | 3.12
1050 |  | 26 32 15.00 | 6 | Test Reports | Inspections | 3.6.3
1051 |  | 26 32 15.00 | 6 | Test Reports | Functional Acceptance Test Procedure | 3.9.6
1052 |  | 26 32 15.00 | 7 | Certificates | Cooling System | 2.8
1053 |  | 26 32 15.00 | 7 | Certificates | Vibration Isolation | 2.1.7
1054 |  | 26 32 15.00 | 7 | Certificates | Prototype Test | 2.29.2
1055 |  | 26 32 15.00 | 7 | Certificates | Reliability and Durability | 2.1.5
1056 |  | 26 32 15.00 | 7 | Certificates | Fuel System Certification | 1.4.11
1057 |  | 26 32 15.00 | 7 | Certificates | Start-Up Engineer | 3.8
1058 |  | 26 32 15.00 | 7 | Certificates | Instructor's Qualification Resume | 3.11.1
1059 |  | 26 32 15.00 | 7 | Certificates | Engine Emission Limits | 2.1.2.1
1060 |  | 26 32 15.00 | 7 | Certificates | Sound Limitations | 2.9
1061 |  | 26 32 15.00 | 7 | Certificates | Site Visit | 3.1
1062 |  | 26 32 15.00 | 7 | Certificates | Current Balance | 2.16.1
1063 |  | 26 32 15.00 | 7 | Certificates | Materials and Equipment | 2.4
1064 |  | 26 32 15.00 | 7 | Certificates | Factory Inspection and Tests | 2.29
1065 |  | 26 32 15.00 | 7 | Certificates | Engine Tests | 3.6.4
1066 |  | 26 32 15.00 | 7 | Certificates | Generator Tests | 3.6.5
1067 |  | 26 32 15.00 | 7 | Certificates | Assembled Engine-Generator Set Tests | 3.6.6
1068 |  | 26 32 15.00 | 10 | Operation and Maintenance Data | Preliminary Assembled Operation and Maintenance Manuals | 3.9.5
1069 |  | 26 32 15.00 | 10 | Operation and Maintenance Data | Posted Data and Instructions | 3.16
1070 |  | 26 32 15.00 | 10 | Operation and Maintenance Data | Training Plan | 3.11.2
1071 |  | 26 51 00 | 2 | Shop Drawings | Luminaire Drawings | 1.5.1
1072 |  | 26 51 00 | 3 | Product Data | Luminaires | 2.2
1073 |  | 26 51 00 | 3 | Product Data | Light Sources | 2.3
1074 |  | 26 51 00 | 3 | Product Data | LED Drivers | 2.4
1075 |  | 26 51 00 | 3 | Product Data | Luminaire Warranty | 1.6.1
1076 |  | 26 51 00 | 3 | Product Data | Exit Signs | 2.5.1
1077 |  | 26 51 00 | 3 | Product Data | Emergency Drivers | 2.5.3
1078 |  | 26 51 00 | 3 | Product Data | Linear LED Lamps | 2.3.1.1
1079 |  | 26 51 00 | 3 | Product Data | Luminaire Design Data | 1.5.2
1080 |  | 26 51 00 | 7 | Certificates | LED Driver and Dimming Switch Compatibility Certificate | 1.5.3
1081 |  | 26 51 00 | 10 | Operation and Maintenance Data | Lighting System | 1.7.1
1082 |  | 26 51 00 | 10 | Operation and Maintenance Data | Maintenance Staff Training Plan | 3.3.1.1
1083 |  | 26 51 00 | 10 | Operation and Maintenance Data | End-User Training Plan | 3.3.1.2
1084 |  | 27 10 00 | 2 | Shop Drawings | Telecommunications Drawings | 1.6.1.1
1085 |  | 27 10 00 | 2 | Shop Drawings | Telecommunications Space Drawings | 1.6.1.2
1086 |  | 27 10 00 | 2 | Shop Drawings | Equipment Support Frame | 2.4.2
1087 |  | 27 10 00 | 3 | Product Data | Telecommunications Cabling | 2.3
1088 |  | 27 10 00 | 3 | Product Data | Patch Panels | 2.4.4
1089 |  | 27 10 00 | 3 | Product Data | Telecommunications Outlet/Connector Assemblies | 2.5
1090 |  | 27 10 00 | 6 | Test Reports | Telecommunications Cabling Testing | 3.5.1
1091 |  | 27 10 00 | 7 | Certificates | Telecommunications Contractor | 1.6.2.1
1092 |  | 27 10 00 | 7 | Certificates | Key Personnel | 1.6.2.2
1093 |  | 27 10 00 | 7 | Certificates | Manufacturer Qualifications | 1.6.2.3
1094 |  | 27 10 00 | 7 | Certificates | Test Plan | 1.6.3
1095 |  | 27 10 00 | 9 | Manufacturer's Field Reports | Factory Reel Tests | 2.10.1
1096 |  | 27 10 00 | 10 | Operation and Maintenance Data | Telecommunications Cabling and Pathway System | 1.10.1
1097 |  | 27 10 00 | 11 | Closeout Submittals | Record Documentation | 1.10.2
1098 |  | 28 31 76 | 1 | Preconstruction Submittals | Fire alarm system designer | 1.8.2.1
1099 |  | 28 31 76 | 1 | Preconstruction Submittals | Supervisor | 1.8.2.2
1100 |  | 28 31 76 | 1 | Preconstruction Submittals | Technician | 1.8.2.3
1101 |  | 28 31 76 | 1 | Preconstruction Submittals | Installer | 1.8.2.4
1102 |  | 28 31 76 | 1 | Preconstruction Submittals | Test Technician | 1.8.2.5
1103 |  | 28 31 76 | 1 | Preconstruction Submittals | Fire Alarm System Site-Specific Software Acknowledgement | 1.7
1104 |  | 28 31 76 | 2 | Shop Drawings | Nameplates | 1.8.1.3
1105 |  | 28 31 76 | 2 | Shop Drawings | Instructions | 2.2.4
1106 |  | 28 31 76 | 2 | Shop Drawings | Wiring Diagrams | 1.8.1.4
1107 |  | 28 31 76 | 2 | Shop Drawings | System Layout | 1.8.1.5
1108 |  | 28 31 76 | 2 | Shop Drawings | Notification Appliances | 1.8.1.6
1109 |  | 28 31 76 | 2 | Shop Drawings | Initiating Devices | 1.8.1.7
1110 |  | 28 31 76 | 2 | Shop Drawings | Amplifiers | 1.8.1.8
1111 |  | 28 31 76 | 2 | Shop Drawings | Battery Power | 1.8.1.9
1112 |  | 28 31 76 | 2 | Shop Drawings | Voltage Drop Calculations | 1.8.1.10
1113 |  | 28 31 76 | 2 | Shop Drawings | Textual Display Sign Control Panel | 2.12.3
1114 |  | 28 31 76 | 3 | Product Data | Fire Alarm and Mass Notification Control Unit (FMCU) | 2.3
1115 |  | 28 31 76 | 3 | Product Data | Local Operating Console (LOC) | 1.4.4
1116 |  | 28 31 76 | 3 | Product Data | Amplifiers | 1.8.1.8
1117 |  | 28 31 76 | 3 | Product Data | Tone Generators | 2.5
1118 |  | 28 31 76 | 3 | Product Data | Digitalized voice generators | 2.5
1119 |  | 28 31 76 | 3 | Product Data | Manual Stations | 2.6
1120 |  | 28 31 76 | 3 | Product Data | Smoke Detectors | 2.7
1121 |  | 28 31 76 | 3 | Product Data | Duct Smoke Detectors | 2.7.2
1122 |  | 28 31 76 | 3 | Product Data | Heat Detectors | 2.8
1123 |  | 28 31 76 | 3 | Product Data | Carbon monoxide detector | 2.9
1124 |  | 28 31 76 | 3 | Product Data | Addressable Interface Devices | 2.1
1125 |  | 28 31 76 | 3 | Product Data | Addressable Control Modules | 2.11
1126 |  | 28 31 76 | 3 | Product Data | Notification Appliances | 1.8.1.6
1127 |  | 28 31 76 | 3 | Product Data | Textual Display Signs | 2.12.3
1128 |  | 28 31 76 | 3 | Product Data | Batteries | 2.14.1
1129 |  | 28 31 76 | 3 | Product Data | Battery Chargers | 2.14.2
1130 |  | 28 31 76 | 3 | Product Data | Supplemental Notification Appliance Circuit Panels | 2.14.1.1
1131 |  | 28 31 76 | 3 | Product Data | Auxiliary Power Supply Panels | 2.14.1.1
1132 |  | 28 31 76 | 3 | Product Data | Surge Protective Devices | 2.15
1133 |  | 28 31 76 | 3 | Product Data | Alarm Wiring | 2.15
1134 |  | 28 31 76 | 3 | Product Data | Back Boxes and Conduit | 3.3.4
1135 |  | 28 31 76 | 3 | Product Data | Ceiling Bridges | 3.2.10
1136 |  | 28 31 76 | 3 | Product Data | Terminal Cabinets | 3.3.2
1137 |  | 28 31 76 | 3 | Product Data | Automatic Fire Alarm Transmitters | 2.18
1138 |  | 28 31 76 | 3 | Product Data | Radio Transmitter and Interface Panels | 2.18.1
1139 |  | 28 31 76 | 3 | Product Data | Mass Notification Transceiver | 2.17.1
1140 |  | 28 31 76 | 3 | Product Data | Electromagnetic Door Holders | 2.19.2
1141 |  | 28 31 76 | 3 | Product Data | Environmental Enclosures or Guards | 2.2
1142 |  | 28 31 76 | 3 | Product Data | Document Storage Cabinet | 3.12.3
1143 |  | 28 31 76 | 6 | Test Reports | Test Procedures | 3.8.1
1144 |  | 28 31 76 | 7 | Certificates | Verification of Compliant Installation | 3.8.2.1
1145 |  | 28 31 76 | 7 | Certificates | Request for Government Final Test | 3.8.2.2
1146 |  | 28 31 76 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | 3.1
1147 |  | 28 31 76 | 10 | Operation and Maintenance Data | Instruction of Government Employees | 3.11
1148 |  | 28 31 76 | 11 | Closeout Submittals | As-Built Drawings | 1.8.1.13
1149 |  | 28 31 76 | 11 | Closeout Submittals | Spare Parts | 1.10.1
1150 |  | 31 00 00 | 3 | Product Data | Utilization of Excavated Materials | 3.6
1151 |  | 31 31 16.19 | 3 | Product Data | Written Warranty | 1.6
1152 |  | 31 31 16.19 | 3 | Product Data | Chemical Soil Treatment | 2.1.1
1153 |  | 31 31 16.19 | 7 | Certificates | Termite Control Company | 1.3
1154 |  | 31 31 16.19 | 8 | Manufacturer's Instructions | Chemical Soil Treatment | 2.1.1
1155 |  | 31 31 16.19 | 11 | Closeout Submittals | Written Warranty | 1.6
1156 |  | 32 16 19 | 3 | Product Data | Concrete | 2.1
1157 |  | 32 16 19 | 3 | Product Data | Biodegradable Form Release Agent | 2.6.5
1158 |  | 32 16 19 | 3 | Product Data | Biodegradable Form Release Agent | 3.2
1159 |  | 32 16 19 | 6 | Test Reports | Field Quality Control | 3.8
1160 |  | 32 31 13 | 2 | Shop Drawings | Fence Assembly | 2.1
1161 |  | 32 31 13 | 2 | Shop Drawings | Location of Gate, Corner, End, and Pull Posts | 3.2.1.1
1162 |  | 32 31 13 | 2 | Shop Drawings | Gate Assembly | 2.1
1163 |  | 32 31 13 | 2 | Shop Drawings | Gate Hardware and Accessories | 2.3.6
1164 |  | 32 31 13 | 2 | Shop Drawings | Erection/Installation Drawings | Part 3
1165 |  | 32 31 13 | 3 | Product Data | Fence Assembly | 2.1
1166 |  | 32 31 13 | 3 | Product Data | Gate Assembly | 2.1
1167 |  | 32 31 13 | 3 | Product Data | Gate Hardware and Accessories | 2.3.6
1168 |  | 32 31 13 | 3 | Product Data | Zinc Coating | 2.4.1
1169 |  | 32 31 13 | 3 | Product Data | Fabric | 2.2.1
1170 |  | 32 31 13 | 3 | Product Data | Stretcher Bars | 2.2.6
1171 |  | 32 31 13 | 3 | Product Data | Concrete | 2.4.2
1172 |  | 32 31 13 | 3 | Product Data | Line Posts | 2.2.2.1.1
1173 |  | 32 31 13 | 3 | Product Data | Braces | 2.2.3
1174 |  | 32 31 13 | 3 | Product Data | Top Rail | 2.2.3.1
1175 |  | 32 31 13 | 3 | Product Data | Wire Ties | 2.2.4
1176 |  | 32 31 13 | 3 | Product Data | Sleeves | 2.2.5
1177 |  | 32 31 13 | 3 | Product Data | Gate Posts | 2.3.1
1178 |  | 32 31 13 | 3 | Product Data | Padlocks | 2.3.5
1179 |  | 32 31 13 | 7 | Certificates | Certificates of Compliance | 1.3.1
1180 |  | 32 31 13 | 7 | Certificates | Recycled Material Content | 3.3
1181 |  | 32 31 13 | 8 | Manufacturer's Instructions | Fence Assembly | 2.1
1182 |  | 32 31 13 | 8 | Manufacturer's Instructions | Gate Assembly | 2.1
1183 |  | 32 31 13 | 8 | Manufacturer's Instructions | Hardware Assembly | 2.1
1184 |  | 32 31 13 | 8 | Manufacturer's Instructions | Accessories | 2.1
1185 |  | 32 92 23 | 3 | Product Data | Fertilizer | 2.4
1186 |  | 32 92 23 | 7 | Certificates | sods | 2.1